## Cover
McLane Company, Inc.
IBM z/OS MAINFRAME — DISASTER RECOVERY PLAYBOOK
Temple (DST) → CoLo (DSC) Site Swap ¦ Dell PowerMax Storage
DOCUMENT CONTROL
Client | McLane Company, Inc.
Document Type | Disaster Recovery Playbook — Mainframe Site Swap
Storage Platform | Dell EMC PowerMax (Arrays 3328 / 3329) ¦ SRDF/RDF Replication
Primary Site | Temple Data Center — JES2 Sysplex (DST)
DR Site | CoLo Data Center — JES2 Sysplex (DSC)
LPARs in Scope | EMER, JESB, JESA, JESC, MV3A/B/C, XCFA00/01, XCFB00/01
MQ Managers | MQPA (MQP2/3), MQTA (MQT2/3), MQGA, MQFA, MQB1
DB2 Subsystems | DBP1/2/3 (Production) DBT1/2/3 (Test) DB2I
Version | 1.0
Classification | CONFIDENTIAL — Internal Use Only
Prepared By
Reviewed By
Approved By
DR Test Date
WORKBOOK STRUCTURE
Cover | Document control, environment overview, LPAR reference, sign-off
DR Steps | Complete step-by-step execution — all phases in sequence with command details
Evidence Log | Consolidated evidence capture for every step — one log to update
ENVIRONMENT REFERENCE — Temple (DST) vs CoLo (DSC)
Component | Temple (DST — Primary) | CoLo (DSC — DR) | Notes
Mainframe | IBM z16 (P00AF008) | IBM z16 — CBU Activated
IODF | SYS2.IODF11 (PROD) | IODF31 (Disaster/Failover)
Sysplex | JES2 (JESB/A/C, MV3B/A/C) | JES2 CoLo (JESB/A/C)
CF LPARs | XCFA00/01, XCFB00/01 | XCFA00/01, XCFB00/01
EMER Load/Parm | 3003 / 3003C0 | 4003 / 4003C3 | Respond 00,c for <8GB
DASD | PowerMax 3329 — MF_JES2P_DST_SG | PowerMax 3328 — MF_JES2P_DSC_SG | RDF R1→R2
JESB Load/Parm | N/A (Primary) | 4460 / 4000F3 | S25R01 / SYSCOM
SYSCOM Vol | N/A | 4000
HMC URL | Existing HMC | https://10.49.35.103
IEF234E URL | https://10.40.22.17/login | https://10.49.22.9/
Unisphere | Array 3329 | Array 3328
LPAR CONFIGURATION REFERENCE (Temple)
LPAR | Proc Assignment | Wt | Init | Res | Mem | ZIIP
XCFB00 | Not Dedicated ICF | 900 | 1 | 1 | 16 GB | n/a
XCFA00 | Not Dedicated ICF | 900 | 1 | 1 | 14 GB | n/a
XCFB01 | Not Dedicated ICF | 100 | 1 | 1 | 6 GB | n/a
XCFA01 | Not Dedicated ICF | 100 | 1 | 1 | 6 GB | n/a
JESB | Unchecked Dedicated | 120 | 3 | 1 | 27 GB | 0/1
JESA | Unchecked Dedicated | 140 | 4 | 1 | 25 GB | 0/1
JESC | Unchecked Dedicated | 18 | 2 | 0 | 10 GB | 0/1
MV3B | Unchecked Dedicated | 8 | 1 | 1 | 6 GB | 0/1
MV3A | Unchecked Dedicated | 4 | 1 | 1 | 6 GB | 0/1
MV3C | Unchecked Dedicated | 2 | 1 | 1 | 6 GB | 0/1
EMER | Unchecked Dedicated | 3 | 1 | 1 | 6 GB | 0/0
DR EXECUTION SIGN-OFF
Phase / Activity | Start Time | End Time | Result | Sign / Initials |  | Notes
Pre-Failover Checklist |  |  | ☐ PASS ☐ FAIL ☐ N/A
MVS3 Sysplex Shutdown |  |  | ☐ PASS ☐ FAIL ☐ N/A
Temple Mainframe Shutdown |  |  | ☐ PASS ☐ FAIL ☐ N/A
Dell PowerMax Failover |  |  | ☐ PASS ☐ FAIL ☐ N/A
CoLo Startup (EMER + JESB IPL) |  |  | ☐ PASS ☐ FAIL ☐ N/A
DB2 Recovery (TEST + PROD) |  |  | ☐ PASS ☐ FAIL ☐ N/A
MQ Recovery (TEST + PROD) |  |  | ☐ PASS ☐ FAIL ☐ N/A
JESA / JESC IPL |  |  | ☐ PASS ☐ FAIL ☐ N/A
CICS Startup |  |  | ☐ PASS ☐ FAIL ☐ N/A
Final Validation |  |  | ☐ PASS ☐ FAIL ☐ N/A
DR OVERALL RESULT |  | ☐ SUCCESS ☐ PARTIAL ☐ FAIL
DR Start Time |  | DR End Time

## DR Steps
McLane — IBM z/OS Mainframe DR Playbook ¦ Step-by-Step Execution
Temple (DST) → CoLo (DSC) ¦ Dell PowerMax ¦ All phases in execution sequence ¦ Columns E–G: fill during execution
# | Phase | Step / Task | Command / Detail | Completed By | Date & Time | Result
PHASE 1 — PRE-FAILOVER CHECKLIST
ℹ ALL items below must be verified BEFORE initiating the site swap. Do not proceed to Phase 2 until all are complete.
1 | Pre-Failover | Confirm with Scheduling — no critical job constraints exist for running past 4am. 5am window is acceptable.
2 | Pre-Failover | Review "Issues and Improvements" log from previous DR test.
3 | Pre-Failover | Confirm all team members have console access assigned (Option B/F/F600/F610/F611/F612 per site).
4 | Pre-Failover | Run DLm Health Check per pre-site swap procedure doc. Ref: "DLm and DataDomain Siteswap procedures pre-check (Business as Usual).docx"
5 | Pre-Failover | Notify Dell (PowerMax / DLm / DataDomain) — open SRs on PMax and DLM. Request standby support.
6 | Pre-Failover | Notify IBM and Mainline — request standby support.
7 | Pre-Failover | Confirm with Customer-Facing and ECOMM — verify MQ jobs have not changed since last DR test.
8 | Pre-Failover | Confirm any new APF/LNKLST libraries added dynamically have been added to PROG30. Compare: SYS1.JES2.Z25.PARMLIB(PROG00, PROG30)
9 | Pre-Failover | Confirm any new OMVS mounts are in BPXPARM member. Compare: SYS1.JES2.Z25.PARMLIB(BPXPRMFP)
10 | Pre-Failover | Confirm any new LPA libraries added dynamically are in LPALST30 (LPA compare).
11 | Pre-Failover | If CFRM policy changes needed — run job SYS3.SMP.SYSPLEX.JES2(POLCFRDR) to apply to PCOUPLE & ACOUPLE.
12 | Pre-Failover HMC | Verify CoLo z16 HMC: Operational Customizations → Customize/Delete Activation Profiles. Validate: XCFB00 = Non-dedicated ICF JESA: CP 4,1 / ZIIP 0,1 / Weight 140 JESB: CP 3,1 / ZIIP 0,1 / Weight 120 JESC: CP 2,0 / ZIIP 0,1 / Weight 18 LPAR/LPAR Group weights match Temple | URL: https://10.49.35.103
13 | Pre-Failover HMC | Confirm time on CoLo HMC: Home → Task Index → Manage System Time UTC -6, 1hr DST offset (-5 from UTC) Validate CLOCK02 = W.05.00.00 Confirm IEASYSD2/3 (Disaster) and IEASYSF2/3 (Failover) all use CLOCK02
14 | Pre-Failover PowerMax | Open Unisphere. Validate Page/Temp volumes in BOTH arrays are in "Ready" status. Temple Array 3329: MF_JES2P_DST_SG CoLo Array 3328: MF_JES2P_DSC_SG Confirm RDF group = Adaptive Copy / Failed Over State (Data Protection tab).
15 | Pre-Failover PowerMax | Validate EMER LPAR Temple is down OR only EMER volumes online. TSO DSP VOL — only these should appear: S24EMR 3003 / S23EMR 3004 / S23EM1 3006 / SYS999 3007 / S24EM1 3008
PHASE 2 — MVS3 SYSPLEX SHUTDOWN (Pre-Swap)
⚠ DO NOT SHUTDOWN JES2 SUBSYSTEM ON MV3B UNTIL JES2 CHECKPOINT OFFLOAD IS COMPLETE
16 | MVS3 Shutdown | Notify QA & Scheduling before beginning any shutdown activity.
17 | MVS3 Shutdown | Shutdown MV3A LPAR.
18 | MVS3 Shutdown | Shutdown MV3C LPAR.
19 | MVS3 Shutdown JES2 Ckpt | MV3B — JES2 CHECKPOINT OFFLOAD (offload CF checkpoint to DASD before CF shutdown). Step 1: Display current state — verify CKPT1 in CF (STRNAME=JES2_MVS3, VOLATILE=YES) | $D CKPTDEF
20 | MVS3 Shutdown JES2 Ckpt | Step 2: Set new CKPT1 target on DASD | $T CKPTDEF,NEWCKPT1=(DSN=SYS1.HASPCKPT,VOL=SYS3M0)
21 | MVS3 Shutdown JES2 Ckpt | Step 3: Verify NEWCKPT1 populated | $D CKPTDEF
22 | MVS3 Shutdown JES2 Ckpt | Step 4: Initiate reconfiguration | $TCKPTDEF,RECONFIG=YES
23 | MVS3 Shutdown JES2 Ckpt | Expected operator responses during reconfiguration: $HASP285 JES2 CHECKPOINT RECONFIGURATION STARTED → Reply: 1 (FORWARD CKPT1 TO NEWCKPT1) $HASP273 → Reply: CONT $HASP280 confirms SYS1.HASPCKPT on SYS3M0 is in use $HASP255 JES2 CHECKPOINT RECONFIGURATION COMPLETE
24 | MVS3 Shutdown JES2 Ckpt | Step 5: Final verify — both CKPT1 and CKPT2 must show VOLATILE=NO (DASD) | $D CKPTDEF
25 | MVS3 Shutdown | Shutdown MV3B LPAR (after Checkpoint Offload confirmed complete, issue $PJES2).
26 | MVS3 Shutdown | Deactivate LPARs: MV3A, MV3B, MV3C.
27 | MVS3 Shutdown | Deactivate CF LPARs: XCFA01, XCFB01.
PHASE 3 — TEMPLE MAINFRAME SHUTDOWN
ℹ Confirm with Operations — no division requests pending before initiating shutdown.
28 | Temple Shutdown Pre-Shutdown | Backup Compuware datasets before shutdown: SYS2.CMPW.LICENSE SYS2.CMPW.LICENSE.CHKPT Note backup dataset name: MT.PERM.CMPW.BKPUP.DR2025
29 | Temple Shutdown Pre-Shutdown | Confirm "sender" channels between PTDCMQ01 and MQPA have been stopped.
30 | Temple Shutdown Pre-Shutdown | Order SHH — update Special Job Schedule table DSSHHSAT. Confirm last-run jobs with Scheduling.
31 | Temple Shutdown Pre-Shutdown | Force job DSTMP01J from schedule (initial TEMP file cleanup). Bypass all conditions, set class Z.
32 | Temple Shutdown MQ | Gather "Before" MQ counts for MQPA from Mainview Explorer. Save to spreadsheet titled "MQP2 Before Shutdown".
33 | Temple Shutdown MQ | Check all MQPA queues with depth — verify message persistence. Run SYS2.SYSTEMS.JOBS(QMMNOPER) — search for BMCQMM309I. Disregard AMQ* queues. Assess and offload non-persistent messages as needed. Note: BMCQMM327W messages are NOT an issue — no action required.
⚠ DO NOT PROCEED WITH MQ SHUTDOWN UNTIL STEPS ABOVE ARE COMPLETE AND VERIFIED
34 | Temple Shutdown MQ | Load MQ Shutdown table. Watch jobs and note anything requiring future attention.
35 | Temple Shutdown MQ | Confirm MQPABKUP job ran as part of MQSSHUT.
36 | Temple Shutdown MQ | CTM/ControlM jobs handle shutdown up to stopping CONTROL-O and running CTMCAJF.
37 | Temple Shutdown IEF234E | Before stopping TSO/SDSF — capture last IEF234E message. Confirm tape made it to CoLo. Example: IEF234E K 0A5F,401215,PVT,DSDISWKB,DSSDUMP - RACK=401215 Validate at CoLo DLm console: https://10.49.22.9/
38 | Temple Shutdown LPARs | Shutdown JESC LPAR — Temple (follow Shutdown Doc).
39 | Temple Shutdown LPARs | Shutdown JESA LPAR — Temple (follow Shutdown Doc).
40 | Temple Shutdown JES2 Ckpt | JESB — JES2 Checkpoint Offload to DASD BEFORE issuing $PJES2. Target volume: SYSM01 | $T CKPTDEF,NEWCKPT1=(DSN=SYS1.HASPCKPT,VOL=SYSM01)
41 | Temple Shutdown JES2 Ckpt | Initiate reconfiguration | $TCKPTDEF,RECONFIG=YES
42 | Temple Shutdown JES2 Ckpt | Final verify — CKPT1 and CKPT2 both VOLATILE=NO | $D CKPTDEF
43 | Temple Shutdown LPARs | Shutdown JESB LPAR — Temple (after Checkpoint Offload confirmed).
44 | Temple Shutdown LPARs | Deactivate: JESC, JESA, JESB LPARs — Temple.
45 | Temple Shutdown LPARs | Deactivate: XCFA00, XCFB00 CF LPARs — Temple.
46 | Temple Shutdown EMER | Startup EMER LPAR Temple for validation: Activate → Load 3003 / Parm 3003C0 (Console MV1AF600). Respond "00,C" when prompted for 8GB memory.
47 | Temple Shutdown EMER | Respond to RACF prompts: 01continue, 02continue.
48 | Temple Shutdown EMER | JES2 init response: 03,warm,noreq. Cancel any IEF238D SMFDUMP prompt.
49 | Temple Shutdown EMER | Issue D A,L — confirm VTAM active. Start TSO. | S TSO
50 | Temple Shutdown EMER | Validate no owed tracks on JES2/MVS3 Storage Groups R0, R10. | S EMCSCF S EMCRDF #SQ VOL,30C0,INV_TRKS
PHASE 4 — DELL POWERMAX STORAGE FAILOVER
ℹ Dell support must be on standby. SRs must be open on PowerMax and DLM before starting.
51 | PowerMax RDF | Initiate PowerMax Reverse Replication — CoLo (R2) → Temple (R1). Execute Steps 1 through 33 ONLY at this stage. Ref: "PowerMax Siteswap procedures DST to DSC - JES2"
52 | PowerMax DD/DLm | SIMULTANEOUSLY — Initiate DD Reverse Replication — CoLo → Temple. Ref: "DLM and DataDomain Siteswap procedures DST to DSC"
53 | PowerMax Network | Network Port Changes: Verify with Network team if any address changes needed. (On most site swaps no action is required — keep for awareness.)
54 | PowerMax CBU | Activate CBU record V05 on CoLo z16 HMC. Update activation profile: ICF: 2 initial / 0 reserved CPU: 5 initial / 0 reserved Confirm LPAR CPU counts: A=4, B=3, C=2 Ref: CBU Activation - 2025.docx
55 | PowerMax CBU | Confirm ZIIP activation. Validate PU count (expect 8 PUs active after ZIIP activation).
PHASE 5 — CoLo MAINFRAME STARTUP
56 | CoLo Startup EMER IPL | Startup EMER LPAR CoLo (IODF — R2s 4x line): Load address: 4003 (S24EMR volume) Load parm: 4003C3 *** Will get <8GB MEMORY PROMPT — Respond: 00,c ***
57 | CoLo Startup EMER IPL | Respond to EMER IPL prompts: 0: 00,u 1: ##,continue (RACF — twice: Primary & Secondary) 2: ##,warm,noreq (JES2 $HASP426) 3: ##,y ($HASP478) 4: S TSO (after D A,L confirms VTAM is up)
58 | CoLo Startup EMER EMC | Validate EMC working. Check owed tracks on JES2/MVS3 Storage Groups R0, R10. | S EMCSCF4 S EMCRDF #SQ VOL,40C0,INV_TRKS
59 | CoLo Startup TEMP Reinit | Verify unit 4200 online (SYS1.DISASTER.CNTL). Verify unit 4000 online (SYSCOM).
60 | CoLo Startup TEMP Reinit | Execute TEMP reinit jobs in this order: SYS1.DISASTER.CNTL(TEMPOFF) SYS1.DISASTER.CNTL(TEMPIN9J) ← verify TEMPIN9U points to UNIT(4xxx) not 3xxx SYS1.DISASTER.CNTL(TEMPONL) SYS1.DISASTER.CNTL(TEMPVVDJ) SYS1.DISASTER.CNTL(TEMPOFF)
61 | CoLo Startup TEMP Reinit | Vary any extra volumes OFFLINE. Only these 5 should remain online: S24EMR 4003 / S23EMR 4004 / S23EM1 4006 / SYS999 4007 / S24EM1 4008 Command: V 4xxx,OFFLINE (e.g., V 4000,OFFLINE for SYSCOM)
62 | CoLo Startup CF & JESB | Activate XCFB00 CF LPAR.
63 | CoLo Startup CF & JESB | Activate JESB, JESA, JESC LPARs.
64 | CoLo Startup CF & JESB | Start JESB F600 Console — CoLo.
65 | CoLo Startup CF & JESB | IPL JESB LPAR (IODF31): Load address: 4460 (S25R01 volume) Load parm: 4000F3 (SYSCOM volume) IPL with CLEAR option Set scroll: K S,DEL=RD (F6 on console) Validate system time is accurate
66 | CoLo Startup IPL Response | IXC420D — Sysplex Initialization response: | R 0,I
67 | CoLo Startup IPL Response | IXC287/288/289 — CFRM Couple Dataset (use COUPLEDR datasets): PRIMARY: SYS1.PLEXDR.JES2Z15.CFRM.PCOUPLE ON SYSM11 ALTERNATE: SYS1.PLEXDR.JES2Z15.CFRM.ACOUPLE ON SYSM10 | R 0,C R 0,U (for PCOUPLE) R 0,U (for ACOUPLE)
68 | CoLo Startup IPL Response | JES2 Initialization — $HASP426 SPECIFY OPTIONS: | R #,WARM,NOREQ
69 | CoLo Startup IPL Response | Multi-Member Integrity Lock — $HASP479: | R #,Y
70 | CoLo Startup IPL Response | If CF policy changed since last failover (load updated policy): | SETXCF START,POLICY,TYPE=CFRM,POLNAME=POLICY02
71 | CoLo Startup IPL Verify | Display network ports — all must show ONLINE: | D M=CHP(FC) D M=CHP(FD) D M=CHP(F8) D M=CHP(F9)
72 | CoLo Startup IPL Verify | Verify OMVS is ACTIVE: | D OMVS
73 | CoLo Startup IPL Verify | Display Coupling Facility structures: | D XCF D XCF,STR D XCF,STR,STRNM=IXCPATH1A
74 | CoLo Startup IPL Verify | Display GRS — must show: GRS STAR MODE, JESB CONNECTED: | D GRS
75 | CoLo Startup IPL Verify | Display SMSVSAM — Status must be GOOD / ACTIVE: PRIM001.VSYSM10 / SPA0001.VSYSM11 / SEC0001.VSYSM11 | D SMS,SHCDS
76 | CoLo Startup IPL Verify | Display RRS Unit of Recovery status — all counts must = 0: | D RRS,URSTATUS
77 | CoLo Startup IPL Verify | Display tape devices — validate all online: | D M=DEV(0A00-0A1F) D M=DEV(0900-091F)
78 | CoLo Startup DLm | Validate DLm VT Status = Running: Login DLm Management Tool → Console → Option 1 (vtcon) Confirm "VT Status: Running" at bottom of log.
79 | CoLo Startup VTAM | Apply ControlM/O rules for JESB IPL: | F CONTROLO,F=SYS2.IOAO.MCLANE.RULES(IPLMINI)
80 | CoLo Startup VTAM | Cleanup TEMP catalog (then manually clean DB2MSUB.TEMP datasets in 3.4): | SYS1.DISASTER.CNTL(DELTMPGN)
81 | CoLo Startup VTAM | Eliminate IST530I / IST532I messages: | F VTAM,IOPD,IOINT=0
82 | CoLo Startup VTAM | Check connectivity (all NICs): | RO *ALL,D NET,TRL
83 | CoLo Startup Network | Run ping test-jesb from Roleswap folder. Contact Network if any IPs do not respond.
84 | CoLo Startup Network | Stop Port 23 listener. Confirm Port 230 listener active. Start InterSession (expires after 30 min without key). | P TCPT3270 S TCPT327X (if not active) S INTSESS
85 | CoLo Startup Network | Ping Linux FTE servers: | TSO PING lpdstpfteco01 TSO PING lpdstpfteag01
86 | CoLo Startup Tape | Run tape READ job against previously created tape: | SYS1.DISASTER.CNTL(DRTPREAD)
87 | CoLo Startup Tape | Run tape WRITE job (DLm). Document tape information for post-test validation. | SYS1.DISASTER.CNTL(DRTPWRTE)
88 | CoLo Startup Tape | Run tape READ job against newly created tape: | SYS1.DISASTER.CNTL(DRTPREAD)
89 | CoLo Startup License | Start HSM: | S HSM
90 | CoLo Startup License | Apply VPS key → Start VPS. Apply ZIP390 Key. Run validation job: | SYS2.SYSTEMS.JOBS.Z2R5.VALID(ZIP01)
91 | CoLo Startup License | Apply RTD key (JESA will be started later in the process).
PHASE 6 — DB2 RECOVERY
⚠ If DRGRECT or DRGRECP SYSTSPRT still has entries other than READY/END after 3 runs — STOP and escalate to DBA.
92 | DB2 Recovery DB2-TEST | Start DB2T subsystems on JESB — wait for each to complete recovery before starting next: | /@DBT1 START DB2 /@DBT2 START DB2 /@DBT3 START DB2
93 | DB2 Recovery DB2-TEST | Submit DRGRECT recovery job. Run until SYSTSPRT contains ONLY "READY" and "END". Maximum 3 runs before escalating. | SYS1.DISASTER.DB2(DRGRECT)
94 | DB2 Recovery DB2-TEST | After DBGRECT1 recovery complete — stop all DB2T subsystems: | /@DBT3 STOP DB2 /@DBT2 STOP DB2 /@DBT1 STOP DB2
95 | DB2 Recovery DB2-TEST | Restart DB2T for production use: | /@DBT1 START DB2
96 | DB2 Recovery DB2-PROD | Start DB2P subsystems on JESB — wait for each recovery before proceeding: | /@DBP1 START DB2 /@DBP2 START DB2 /@DBP3 START DB2
97 | DB2 Recovery DB2-PROD | Submit DRGRECP recovery job. Run until SYSTSPRT = READY/END only. Maximum 3 runs. | SYS1.DISASTER.DB2(DRGRECP)
98 | DB2 Recovery DB2-PROD | After DBGRECP1 recovery complete — stop all DB2P subsystems: | /@DBP3 STOP DB2 /@DBP2 STOP DB2 /@DBP1 STOP DB2
99 | DB2 Recovery DB2-PROD | Restart DB2P for production use: | /@DBP1 START DB2
100 | DB2 Recovery DB2I | Repeat DB2 recovery procedure for DB2I subsystems AFTER all other subsystems are up and confirmed stable.
PHASE 7 — MQ RECOVERY
ℹ Watch for tape mount / HSM requests throughout — CONTROL-O is not active during this phase.
101 | MQ Recovery MQTA | Start MQT2MSTR (also starts MQT2CHIN): | /MQT2 START QMGR
102 | MQ Recovery MQTA | Expect: CSQE035E — Structure in failed state, recovery needed (normal). Filter: se - x all;f CSQE035E all
103 | MQ Recovery MQTA | Recover MQTA CF structures. Wait for CSQE131I for each structure. Note: ME structure failure is EXPECTED — not an error. Filter in MQT2MSTR: se - x all;f CSQE131I all | OPR.PERM.CNTL(MQSRECT2)
104 | MQ Recovery MQTA | After MQT2 recovery complete — start MQT3: | /MQT3 START QMGR
105 | MQ Recovery MQTA | Check for recovery messages on MQT3 (should be none after MQT2 recovery). Then stop both: | /MQT2 STOP QMGR /MQT3 STOP QMGR
106 | MQ Recovery MQTA | After both stopped — restart MQT2: | /MQT2 START QMGR
107 | MQ Recovery MQTA | After MQT2 is up — start TEST MQ Trigger monitor: | /S MQTRGYYB
108 | MQ Recovery MQPA | Start MQP2MSTR (also starts MQP2CHIN): | /MQP2 START QMGR
109 | MQ Recovery MQPA | Recover MQPA CF structures. Wait for CSQE131I for each structure. | OPR.PERM.CNTL(MQSRECP2)
110 | MQ Recovery MQPA | After MQP2 recovery — start MQP3. Check for recovery messages (should be none). | /MQP3 START QMGR
111 | MQ Recovery MQPA | After MQP3 fully started — stop both: | /MQP2 STOP QMGR /MQP3 STOP QMGR
112 | MQ Recovery MQPA | After both stopped — restart MQP2: | /MQP2 START QMGR
113 | MQ Recovery MQPA | After MQP2 complete — backup MQPA CF structures. Confirm MQPABKUP job ran successfully. | /S MQPABKUP
114 | MQ Recovery MQPA | Start PROD MQ Trigger monitor: | /S MQTRGXXB
115 | MQ Recovery Non-QSG | Start MQGAMSTR. After CSQU012I from MQGACHIN — start MQGA Agent: | /MQGA START QMGR /S MQGAAGT
116 | MQ Recovery Non-QSG | Start MQFAMSTR. After CSQU012I from MQFACHIN — start MQFA Agent: | /MQFA START QMGR /S MQFAAGT
117 | MQ Recovery Non-QSG | Start MQB1MSTR: | /MQB1 START QMGR
118 | MQ Recovery Non-QSG | Start Mainview. Confirm all Queue Managers are visible. | S MVSTART
119 | MQ Recovery Queue Count | Gather "After" MQ counts for MQPA from Mainview Explorer. Save to spreadsheet: "MQP2 After Recovery". Compare against Before counts — note any unexpected differences.
PHASE 8 — JESA / JESC IPL
120 | JESA/JESC JESB Final | Run started task validation on JESB before proceeding: | SYS2.SYSTEMS.JOBS(STCVER)
121 | JESA/JESC JESB Final | Complete PowerMax Reverse Replication — Steps 34+ to resume CoLo → Temple sync. Ref: "PowerMax Siteswap procedures DST to DSC - JES2"
122 | JESA/JESC JESB Final | Suspend Snapshot policies in CoLo.
123 | JESA/JESC JESA IPL | Start JESA F600 Console.
124 | JESA/JESC JESA IPL | IPL JESA LPAR (IODF31): Load address: 4460 (S25R01) Load parm: 4000F3 (SYSCOM) IPL CLEAR ¦ K S,DEL=RD ¦ Validate time
125 | JESA/JESC JESA IPL | Apply ControlM rules for JESA: | F CONTROLO,F=SYS2.IOAO.MCLANE.RULES(IPLSECND)
126 | JESA/JESC JESC IPL | IPL JESC LPAR (IODF31): Load address: 4460 (S25R01) Load parm: 4000F3 (SYSCOM) IPL CLEAR ¦ K S,DEL=RD ¦ Validate time
127 | JESA/JESC JESC IPL | Apply ControlM rules for JESC: | F CONTROLO,F=SYS2.IOAO.MCLANE.RULES(IPLJESC)
128 | JESA/JESC Validation | Validate ALL expected started tasks on JESA and JESC BEFORE starting CICS: | SYS2.SYSTEMS.JOBS(STCVER)
129 | JESA/JESC Validation | Run PING tests for JESA and JESC. Contact Network if any IPs do not respond. | ping test-jesa ping test-jesc
PHASE 9 — CICS STARTUP
130 | CICS | Start PROD & TEST TSQ and CMSA tasks. Wait for "CMAS initialization complete". | /S J,N=CICSGO1
131 | CICS | Start PROD & TEST WUSA and APPL tasks. Wait for "CICSPlex SM Web User Interface initialization complete". Check regions: CIPSB1, CIPSB2, CIDSB1, CICE. | /S J,N=CICSGO2
132 | CICS | Start PROD & TEST Terminal tasks. Check: CIPSTB, CIDSTB. | /S J,N=CICSGO3
133 | CICS | Initialize EXCI interface on non-JESC LPARs (submits M1MBCJB and M1MBCJA). Verify job completes successfully. | /S J,N=CICSGO4
134 | CICS | Initialize Temporary Storage. Verify successful completion. | MC.PERM.JCL(DSTSQ01J)
135 | CICS | Run CICS open files and TCP initialization jobs after CICS is up: OPR.PRM.CNTL: SSY0OPEN, NRIOPEN, CICSTCP
PHASE 10 — FINAL VALIDATION & POST-SWAP
136 | Final Validation | Run started task validation on ALL LPARs. All expected tasks must be running. | SYS2.SYSTEMS.JOBS(STCVER)
137 | Final Validation | Review DUMP datasets — determine action: Clear or send to IBM.
138 | Final Validation | Run end-to-end ping tests from desktop (all NICs on each LPAR): | ping test-jesb ping test-jesa ping test-jesc
139 | Final Validation | Run FTE Big Test (Z2L and L2Z). Backup file: DSN=MT.PERM.ZSERIES.BIGFILE.TEST.FROM.COLO.D251019 | SYS2.SYSTEMS.JOBS(FTEBIGV)
140 | Final Validation | Validate DB2TOOLS via TSO — query BE3T or equivalent subsystem.
141 | Final Validation | Verify MQ message flows are operational. Compare Before vs After queue counts.

## Evidence Log
McLane — Mainframe DR Playbook ¦ EVIDENCE LOG ¦ Fill this sheet during execution
One row per step. Result: type PASS / FAIL / N/A. Evidence: paste system output, screenshot reference, or observation.
# | Phase | Step Summary | Completed By | Date & Time | Result | Evidence / Notes / Screenshot Ref
1 | Pre-Failover | Scheduling confirmed — 5am window accepted, DSMQTRG noted
2 | Pre-Failover | Issues & Improvements log from previous DR reviewed
3 | Pre-Failover | All team console access confirmed (F600/F611/F612 per site)
4 | Pre-Failover | DLm Health Check completed per pre-swap procedure doc
5 | Pre-Failover | Dell notified — SRs opened on PowerMax and DLM
6 | Pre-Failover | IBM and Mainline notified — standby support confirmed
7 | Pre-Failover | Customer-Facing/ECOMM confirmed — MQ jobs unchanged
8 | Pre-Failover | APF/LNKLST libraries confirmed in PROG30
9 | Pre-Failover | OMVS mounts confirmed in BPXPARM member
10 | Pre-Failover | LPA libraries confirmed in LPALST30
11 | Pre-Failover | CFRM policy changes applied (if applicable)
12 | Pre-Failover / HMC | CoLo HMC LPAR CPU/ZIIP/Weight settings validated
13 | Pre-Failover / HMC | CoLo HMC time confirmed — UTC-5, CLOCK02 = W.05.00.00
14 | Pre-Failover / PowerMax | Unisphere — both arrays Ready, RDF = Adaptive Copy Failed Over
15 | Pre-Failover / PowerMax | EMER volumes validated — only 5 EMER packs online in Temple
16 | MVS3 Shutdown | QA & Scheduling notified before shutdown
17 | MVS3 Shutdown | MV3A LPAR shutdown
18 | MVS3 Shutdown | MV3C LPAR shutdown
19 | MVS3 / JES2 Ckpt | $D CKPTDEF — CKPT1 in CF confirmed (VOLATILE=YES)
20 | MVS3 / JES2 Ckpt | $T CKPTDEF — NEWCKPT1 set to SYS1.HASPCKPT VOL=SYS3M0
21 | MVS3 / JES2 Ckpt | $D CKPTDEF — NEWCKPT1 populated confirmed
22 | MVS3 / JES2 Ckpt | $TCKPTDEF RECONFIG=YES initiated
23 | MVS3 / JES2 Ckpt | Checkpoint reconfiguration responses — $HASP255 COMPLETE
24 | MVS3 / JES2 Ckpt | $D CKPTDEF — final verify both CKPT1/CKPT2 VOLATILE=NO
25 | MVS3 Shutdown | MV3B LPAR shutdown after checkpoint offload confirmed
26 | MVS3 Shutdown | MV3A/B/C LPARs deactivated
27 | MVS3 Shutdown | XCFA01/XCFB01 CF LPARs deactivated
28 | Temple Shutdown | Compuware datasets backed up — MT.PERM.CMPW.BKPUP.DR2025
29 | Temple Shutdown | PTDCMQ01 → MQPA sender channels confirmed stopped
30 | Temple Shutdown | SHH Special Job Schedule updated — DSSHHSAT confirmed
31 | Temple Shutdown | DSTMP01J forced — TEMP cleanup complete
32 | Temple Shutdown | "MQP2 Before Shutdown" queue counts saved
33 | Temple Shutdown | MQPA queue depth/persistence verified — non-persistent offloaded
34 | Temple Shutdown | MQ Shutdown table loaded — jobs monitored
35 | Temple Shutdown | MQPABKUP confirmed ran as part of MQSSHUT
36 | Temple Shutdown | CTM/ControlM shutdown to CONTROL-O/CTMCAJF complete
37 | Temple Shutdown | Last IEF234E captured — RACK ID noted, tape at CoLo confirmed
38 | Temple Shutdown | JESC LPAR shutdown
39 | Temple Shutdown | JESA LPAR shutdown
40 | Temple / JES2 Ckpt | $T CKPTDEF NEWCKPT1 set to SYSM01
41 | Temple / JES2 Ckpt | $TCKPTDEF RECONFIG=YES — JESB checkpoint offloaded
42 | Temple / JES2 Ckpt | $D CKPTDEF final verify — both VOLATILE=NO
43 | Temple Shutdown | JESB LPAR shutdown
44 | Temple Shutdown | JESC/JESA/JESB LPARs deactivated
45 | Temple Shutdown | XCFA00/XCFB00 CF LPARs deactivated
46 | Temple / EMER | EMER Temple IPL — Load 3003/Parm 3003C0 — responded 00,c
47 | Temple / EMER | EMER RACF prompts — 01continue/02continue responded
48 | Temple / EMER | EMER JES2 init — 03,warm,noreq — SMFDUMP cancelled if prompted
49 | Temple / EMER | D A,L — VTAM active — S TSO started
50 | Temple / EMER | EMC validated — EMCSCF/EMCRDF started — no owed tracks
51 | PowerMax | PowerMax RDF Reverse Replication Steps 1–33 complete
52 | PowerMax | DD/DLm Reverse Replication initiated (parallel)
53 | PowerMax / Network | Network port changes assessed — action taken if needed
54 | PowerMax / CBU | CBU record V05 activated — ICF/CPU profile updated
55 | PowerMax / CBU | ZIIP confirmed active — 8 PUs validated
56 | CoLo Startup | EMER CoLo IPL — Load 4003/Parm 4003C3 — responded 00,c
57 | CoLo Startup | EMER IPL prompts responded (00,u / RACF / warm,noreq / $HASP478)
58 | CoLo Startup | EMC validated — EMCSCF4/EMCRDF — no owed tracks on CoLo
59 | CoLo Startup | Units 4200 and 4000 online confirmed
60 | CoLo Startup | TEMP reinit jobs run (TEMPOFF/TEMPIN9J/TEMPONL/TEMPVVDJ/TEMPOFF) — TEMPIN9U points to 4xxx
61 | CoLo Startup | Extra volumes varied offline — only 5 EMER packs remain online
62 | CoLo Startup | XCFB00 CF LPAR activated
63 | CoLo Startup | JESB/JESA/JESC LPARs activated
64 | CoLo Startup | JESB F600 Console started
65 | CoLo Startup | JESB IPL — Load 4460/Parm 4000F3 — CLEAR — time validated
66 | CoLo / IPL Response | IXC420D — R 0,I responded
67 | CoLo / IPL Response | IXC287/288/289 CFRM responses — R 0,C / R 0,U / R 0,U
68 | CoLo / IPL Response | $HASP426 JES2 init — R #,WARM,NOREQ
69 | CoLo / IPL Response | $HASP479 integrity lock — R #,Y
70 | CoLo / IPL Response | CF policy loaded if required (SETXCF POLICY02)
71 | CoLo / IPL Verify | Network ports FC/FD/F8/F9 — all ONLINE
72 | CoLo / IPL Verify | D OMVS — shows ACTIVE
73 | CoLo / IPL Verify | D XCF / D XCF,STR / D XCF,STR,STRNM=IXCPATH1A — structures allocated
74 | CoLo / IPL Verify | D GRS — GRS STAR MODE / JESB CONNECTED
75 | CoLo / IPL Verify | D SMS,SHCDS — all SHCDS datasets GOOD / ACTIVE
76 | CoLo / IPL Verify | D RRS,URSTATUS — all UR counts = 0
77 | CoLo / IPL Verify | D M=DEV tape devices — all online
78 | CoLo / DLm | DLm VT Status = Running confirmed
79 | CoLo / VTAM | F CONTROLO IPLMINI rules applied
80 | CoLo / VTAM | DELTMPGN cleanup complete — DB2MSUB.TEMP cleaned in 3.4
81 | CoLo / VTAM | F VTAM,IOPD,IOINT=0 — IST530I/IST532I suppressed
82 | CoLo / VTAM | RO *ALL,D NET,TRL — connectivity checked
83 | CoLo / Network | ping test-jesb — all IPs respond
84 | CoLo / Network | TCPT3270 stopped / TCPT327X active / INTSESS started
85 | CoLo / Network | TSO PING lpdstpfteco01 and lpdstpfteag01 — respond
86 | CoLo / Tape | Tape READ job against previous tape — complete
87 | CoLo / Tape | Tape WRITE job (DRTPWRTE) — tape info documented
88 | CoLo / Tape | Tape READ job against new tape — complete
89 | CoLo / License | HSM started — S HSM
90 | CoLo / License | VPS key applied / VPS started / ZIP390 key applied / validation job run
91 | CoLo / License | RTD key applied
92 | DB2 Recovery | /@DBT1/2/3 START DB2 — all three started, recovery complete
93 | DB2 Recovery | DRGRECT submitted — SYSTSPRT = READY/END only
94 | DB2 Recovery | /@DBT3/2/1 STOP DB2 — all stopped after recovery
95 | DB2 Recovery | /@DBT1 START DB2 — restarted for use
96 | DB2 Recovery | /@DBP1/2/3 START DB2 — all three started, recovery complete
97 | DB2 Recovery | DRGRECP submitted — SYSTSPRT = READY/END only
98 | DB2 Recovery | /@DBP3/2/1 STOP DB2 — all stopped after recovery
99 | DB2 Recovery | /@DBP1 START DB2 — restarted for use
100 | DB2 Recovery | DB2I recovery complete (after all other subsystems confirmed)
101 | MQ Recovery | /MQT2 START QMGR — CSQE035E structures in failed state (expected)
102 | MQ Recovery | MQSRECT2 submitted — CSQE131I received for all structures
103 | MQ Recovery | /MQT3 START QMGR — no recovery messages (expected)
104 | MQ Recovery | /MQT2 STOP / /MQT3 STOP — both down
105 | MQ Recovery | /MQT2 START QMGR — restarted
106 | MQ Recovery | /S MQTRGYYB — TEST trigger monitor started
107 | MQ Recovery | /MQP2 START QMGR started
108 | MQ Recovery | MQSRECP2 submitted — CSQE131I received for all structures
109 | MQ Recovery | /MQP3 START QMGR — no recovery messages
110 | MQ Recovery | /MQP2 STOP / /MQP3 STOP — both down
111 | MQ Recovery | /MQP2 START QMGR — restarted
112 | MQ Recovery | /S MQPABKUP — backup confirmed complete
113 | MQ Recovery | /S MQTRGXXB — PROD trigger monitor started
114 | MQ Recovery | /MQGA START QMGR / /S MQGAAGT — started
115 | MQ Recovery | /MQFA START QMGR / /S MQFAAGT — started
116 | MQ Recovery | /MQB1 START QMGR — started
117 | MQ Recovery | S MVSTART — all Queue Managers visible in Mainview
118 | MQ Recovery | "MQP2 After Recovery" counts saved — Before/After comparison done
119 | JESA/JESC IPL | JESB STCVER — all started tasks running
120 | JESA/JESC IPL | PowerMax Reverse Replication Steps 34+ complete — sync resumed
121 | JESA/JESC IPL | CoLo Snapshot policies suspended
122 | JESA/JESC IPL | JESA F600 Console started
123 | JESA/JESC IPL | JESA IPL — Load 4460/Parm 4000F3 — CLEAR — time validated
124 | JESA/JESC IPL | F CONTROLO IPLSECND rules applied to JESA
125 | JESA/JESC IPL | JESC IPL — Load 4460/Parm 4000F3 — CLEAR — time validated
126 | JESA/JESC IPL | F CONTROLO IPLJESC rules applied to JESC
127 | JESA/JESC IPL | STCVER on JESA and JESC — all tasks running before CICS
128 | JESA/JESC IPL | Ping test-jesa and ping test-jesc — all IPs respond
129 | CICS | /S J,N=CICSGO1 — CMAS "initialization complete"
130 | CICS | /S J,N=CICSGO2 — WUI "initialization complete" / CIPSB1/2/CIDSB1/CICE verified
131 | CICS | /S J,N=CICSGO3 — Terminal tasks started / CIPSTB/CIDSTB verified
132 | CICS | /S J,N=CICSGO4 — EXCI initialized / M1MBCJB/M1MBCJA complete
133 | CICS | DSTSQ01J — Temporary Storage initialized
134 | CICS | SSY0OPEN / NRIOPEN / CICSTCP — CICS files open / TCP initialized
135 | Final Validation | STCVER on ALL LPARs — all expected tasks running
136 | Final Validation | DUMP datasets reviewed — action taken (clear/IBM)
137 | Final Validation | Pings test-jesb/jesa/jesc — all NICs respond
138 | Final Validation | FTEBIGV — FTE Z2L/L2Z big file test complete
139 | Final Validation | DB2TOOLS via TSO — BE3T query successful
140 | Final Validation | MQ message flows operational — Before/After counts compared