ENTERPRISE DISASTER RECOVERY FAILOVER PLAYBOOK TABLE OF CONTENTS ¦ Version 1.0 ¦ CONFIDENTIAL

| █ Section Heading | • Sub-Section (Level 1) | ◦ Sub-Section (Level 2) |
| --- | --- | --- |

| Section 1 | Executive Summary 4 |
| --- | --- |
| 1.1 | Objective of the Playbook 4 |
| 1.2 | Scope — Systems & Technology Layers Covered 4 |
| 1.3 | DR Trigger Scenarios 4 |
| Section 2 | DR Activation Criteria 5 |
| 2.1 | Activation Thresholds 5 |
| 2.2 | Escalation Matrix 5 |
| Section 3 | Governance & Command Structure 6 |
| 3.1 | War Room Setup 6 |
| 3.2 | RACI — Roles & Responsibilities 6 |
| 3.3 | Communication Plan 6 |
| Section 4 | High-Level Failover Strategy 7 |
| 4.1 | Recovery Model 7 |
| 4.2 | Target RTO / RPO by Tier (from BIA) 7 |
| 4.3 | Data Replication Overview 7 |
| Section 5 | End-to-End Failover Sequence 8 |
| 5.1 | Failover Sequence Overview 8 |
| 5.2 | Validation Checkpoint Register 8 |
| Section 6 | Detailed Step-by-Step Runbooks (Layer-Wise) 9 |
| 6.1 | Storage Runbook — SAN/NAS Failover 9 |
| 6.2 | VMware / Zerto Runbook 9 |
| 6.3 | Network Runbook — Firewall, Load Balancer, Routing 10 |
| 6.4 | DNS & Active Directory Runbook 10 |
| 6.5 | Database Runbook — Oracle, Exadata, SQL Server, DB2 11 |
| 6.5.1 | Oracle Data Guard Failover 11 |
| 6.5.2 | Oracle Exadata Specific Steps 11 |
| 6.5.3 | SQL Server Always On Failover 12 |
| 6.5.4 | DB2 pureScale Failover 12 |
| 6.6 | Middleware Runbook — WebSphere & MQ 12 |
| 6.7 | Application Layer Runbook 13 |
| 6.8 | Mainframe Runbook — IBM zSeries & iSeries (AS400) 13 |
| 6.8.1 | zSeries (z/OS) 13 |
| 6.8.2 | iSeries / AS400 (IBM i) 14 |
| 6.9 | Job Scheduling Runbook — BMC Control-M 14 |
| Section 7 | Dependency Mapping & Application Grouping 15 |
| 7.1 | Tier-wise Recovery Groups 15 |
| 7.2 | Critical Dependency Chain 15 |
| Section 8 | Validation & Sign-off 16 |
| 8.1 | Technical Validation Checklist 16 |
| 8.2 | Business Validation (UAT-Level Checks) 16 |
| 8.3 | Final DR Operational Sign-off 16 |
| Section 9 | Communication Templates 17 |
| Template 1 | DR Invocation Notification 17 |
| Template 2 | 60-Minute Status Update 17 |
| Section 10 | Risks & Known Constraints 18 |
| 10.1 | DR Risk Register 18 |
| 10.2 | Known Manual Interventions Required 18 |
| Section 11 | Failback Strategy (High Level) 19 |
| 11.1 | Conditions for Failback 19 |
| 11.2 | Failback Sequence Overview 19 |
| Section 12 | Failover Timeline View (Hour-by-Hour) 20 |
| 12.1 | Target Timeline — Tier-0 RTO: 4 Hours ¦ Tier-1 RTO: 8 Hours 20 |
| Section 13 | Single-Page DR Execution Dashboard 21 |
| Appendix A | Contact List 22 |
| Appendix B | Tooling References 22 |
| Appendix C | DR Drill Learnings Log 23 |

Note: Page numbers are indicative references to the DR Failover Playbook v1.0. For navigation, use the master playbook document with bookmarked headings.

ENTERPRISE DISASTER RECOVERY

FAILOVER PLAYBOOK

On-Premise Data Center Environment

DR Enablement Program ¦ Disaster Recovery Execution Document Classification: CONFIDENTIAL ¦ Version: 1.0 ¦ Status: APPROVED FOR EXECUTION

| Document Owner | DR Program Director / CTO Office |
| --- | --- |
| Approver | Chief Technology Officer / CISO |
| Document Version | 1.0 — Production Release |
| Review Cycle | Quarterly / Post-DR Drill / Post-Incident |
| Alignment | ISO 22301 ¦ NIST SP 800-34 ¦ ITIL v4 ¦ COBIT 2019 |

# Section 1 — Executive Summary

## 1.1  Objective of the Playbook

This Enterprise DR Failover Playbook constitutes the primary execution document governing the orchestrated recovery of on-premise data-center workloads to the designated Disaster Recovery (DR) site. It operationalizes the organization's DR Strategy and translates Business Impact Analysis (BIA) outcomes into actionable, sequenced technical and governance procedures.

The playbook is designed to serve three audiences simultaneously:

- Incident Commander & Senior Leadership — governance checkpoints, decision authority, and status visibility

- Infrastructure & Platform Teams — layer-specific technical runbooks with pre-conditions, execution steps, and validation

- Application & Business Teams — application recovery sequencing, dependency awareness, and business validation criteria

## 1.2  Scope — Systems & Technology Layers Covered

| # | Technology Layer | Components in Scope |
| --- | --- | --- |
| 1 | Storage | SAN (Fibre Channel), NAS (NFS/CIFS), Synchronous & Asynchronous Replication, Snapshots (NetApp/EMC) |
| 2 | Virtualization | VMware vSphere 7.x / 8.x, vCenter, ESXi Hosts, vSAN, SRM (Site Recovery Manager) |
| 3 | Network | Core/Distribution Switches, Firewalls (Palo Alto/Cisco ASA), Load Balancers (F5/NSX ALB), BGP/OSPF Routing |
| 4 | DNS / IPAM | Primary/Secondary DNS, Split-brain DNS, IPAM (Infoblox) |
| 5 | Identity & Access | Active Directory (AD DS, AD FS, Azure AD Connect), LDAP, PAM |
| 6 | Databases | Oracle 19c RAC, Oracle Exadata X8/X9, SQL Server Always On, DB2 pureScale |
| 7 | Middleware | IBM WebSphere Application Server (Traditional & Liberty), MQ Series |
| 8 | Applications | Tiered enterprise applications (ERP, CRM, Custom), dependency-mapped |
| 9 | Job Scheduling | BMC Control-M (Distributed & z/OS), batch dependency chains |
| 10 | Mainframe | IBM zSeries (z16), iSeries / AS400 (IBM i Power10) |

## 1.3  DR Trigger Scenarios

This playbook is invocable under any of the following declared disaster scenarios:

| Scenario Category | Examples | Expected Impact |
| --- | --- | --- |
| Facility / Physical | Fire, flood, power failure, HVAC failure | Complete loss of Primary DC |
| Cyber / Security | Ransomware, destructive malware, DDoS | Data corruption, system unavailability |
| Infrastructure Failure | SAN failure, network fabric collapse, HW failure | Loss of critical workloads |
| Natural Disaster | Earthquake, typhoon, regional power grid loss | Multi-system unavailability |
| Human Error / Change Failure | Accidental deletion, failed change causing outage | Application/data loss |

# Section 2 — DR Activation Criteria

## 2.1  Activation Thresholds

DR is formally invoked when one or more of the following conditions are met and validated by the Incident Commander in consultation with the Crisis Management Team:

| Threshold | Condition | Authority to Declare |
| --- | --- | --- |
| RTO Breach Imminent | System unavailability projected to exceed BIA-defined RTO within 2 hours | Incident Commander + CTO |
| Confirmed Total Site Loss | Primary DC physically inaccessible or destroyed | CTO / CEO |
| Tier-0 / Tier-1 Unavailability | All Tier-0 or >50% Tier-1 applications offline >1 hour | Incident Commander |
| Data Integrity Compromise | Confirmed ransomware or destructive event impacting production data | CISO + CTO |
| Infrastructure Non-Recoverable | Storage or network layer confirmed non-recoverable in RTO window | Infra Lead + CTO |

## 2.2  Escalation Matrix

| Time Elapsed | Action Required | Escalation To | Decision |
| --- | --- | --- | --- |
| 0–30 min | Incident triage & classification | IT Operations Manager | Engage Infra war room |
| 30–60 min | Incident severity confirmed | Incident Commander | Declare Major Incident |
| 60–90 min | Recovery path assessed | CTO + CISO | Invoke DR Standby |
| 90–120 min | RTO at risk | CEO + Board Liaison | Declare Disaster; Invoke Failover |
| Post-Declaration | Playbook activated | DR Program Director | Execute this playbook |

CRITICAL — Non-Negotiable Pre-Requisite DR must NOT be invoked without written (email / chat-logged) authorization from the designated Decision Authority. Unauthorized failover is considered a change management violation and may result in avoidable data loss.

# Section 3 — Governance & Command Structure

## 3.1  War Room Setup

Upon DR Declaration, the following war room structure is immediately activated:

- Primary War Room: DR Command Center — Building B, Floor 2, Room 204 (or virtual Bridge: [Dial-in TBD])

- Bridge Line: WebEx / Teams bridge — dedicated DR Bridge code activated by IT Ops

- Command Duration: War room remains active until all Tier-0 and Tier-1 applications are validated as operational at DR site

- Cadence: Status update every 30 minutes to Incident Commander; 60-minute executive briefings

## 3.2  RACI — Roles & Responsibilities

| Role / Activity | Incident Cmdr | Infra Lead | App Lead | DB Lead | Network Lead | Bus. Owner |
| --- | --- | --- | --- | --- | --- | --- |
| Declare DR | A | C | I | I | I | C |
| Activate War Room | R | R | I | I | I | I |
| Storage Failover | I | A | I | C | I | I |
| VMware / SRM Failover | I | A | I | I | I | I |
| Network Cutover | I | R | I | I | A | I |
| DNS Cutover | I | R | I | I | A | I |
| AD / Identity Recovery | I | A | R | I | I | I |
| Database Failover | I | C | I | A | I | I |
| Middleware Recovery | I | I | A | C | I | I |
| App Recovery & Sequencing | C | I | A | C | I | C |
| Mainframe Failover | I | C | I | I | C | I |
| Control-M Cutover | I | I | A | I | I | I |
| Business Validation | C | I | C | I | I | A |
| Failover Sign-off | A | R | R | R | R | C |

R=Responsible | A=Accountable | C=Consulted | I=Informed

## 3.3  Communication Plan

| Audience | Channel | Frequency | Owner |
| --- | --- | --- | --- |
| War Room Teams | Teams Bridge / WebEx | Continuous | Incident Commander |
| Executive Leadership | Email + Phone | Every 60 mins | DR Program Director |
| Business Units | Email + Intranet Portal | Every 90 mins | Business Continuity Lead |
| All Staff | Intranet / SMS Broadcast | At declaration + key milestones | Corp Comms |
| Regulators / Customers | Formal Letter / Hotline | Per regulatory obligation | Legal / Compliance |

# Section 4 — High-Level Failover Strategy

## 4.1  Recovery Model

| Parameter | Primary Site (Production) | DR Site (Recovery) |
| --- | --- | --- |
| Model | Active | Passive (Warm Standby) |
| Location | Primary Data Center — [City A] | DR Data Center — [City B] (>100km separation) |
| Connectivity | N/A | Dual 10Gbps MPLS + 1Gbps Internet VPN backup |
| Storage Replication | Source (EMC SRDF Sync / NetApp SnapMirror) | Target (Async within 30-min RPO) |
| VMware | Production vCenter Cluster | DR vCenter + SRM Recovery Plans |
| Network | BGP AS Primary | BGP AS Secondary (pre-staged) |
| Mainframe | z16 Production LPAR | DR z16 LPAR (pre-configured, warm) |

## 4.2  Target RTO / RPO by Tier (from BIA)

| Tier | Description | RTO | RPO | Example Systems |
| --- | --- | --- | --- | --- |
| Tier 0 | Mission-Critical (life-safety / regulatory) | 1 hour | 0 (sync) | Core Banking, Payment Gateway |
| Tier 1 | Business-Critical | 4 hours | 15–30 min | ERP, CRM, AD, DNS |
| Tier 2 | Business-Important | 8 hours | 2 hours | HR Systems, Reporting |
| Tier 3 | Non-Critical / Deferrable | 24–48 hours | 24 hours | Archive, Dev/Test mirrors |

## 4.3  Data Replication Overview

- SAN (EMC SRDF): Synchronous replication for Tier-0 LUNs (zero RPO). Asynchronous for Tier-1/2 (15–30 min delta).

- NetApp SnapMirror: Asynchronous replication for NAS volumes; RPO governed by replication schedule (15-min intervals).

- Oracle Data Guard: Maximum Availability mode for Tier-0 Oracle DBs; Maximum Performance for Tier-1.

- SQL Server Always On: Synchronous replica at DR site for Tier-0/1 SQL workloads.

- VMware SRM: Orchestrates VM protection groups with automated recovery plans; integrated with storage replication.

- Mainframe GDPS / XRC: zSeries uses GDPS (Geographically Dispersed Parallel Sysplex) for continuous journal-based replication.

# Section 5 — End-to-End Failover Sequence

## 5.1  Failover Sequence Overview

The failover sequence follows a strict dependency-ordered layered approach. No layer may proceed without the completion and sign-off of all prerequisite layers. Each phase concludes with a formal Validation Checkpoint (VC) before the next phase commences.

| Seq | Phase | Layer | Owner | Duration | Dependency / VC |
| --- | --- | --- | --- | --- | --- |
| 0 | Pre-Failover | Governance & Preparation | Incident Cmdr | 0–30 min | DR Declaration confirmed — VC-0 |
| 1 | Infra — Storage | SAN/NAS, Replication Break | Infra Lead (Storage) | 30–60 min | VC-0 complete — VC-1 |
| 2 | Infra — Compute | VMware / SRM Recovery Plan | Infra Lead (VMware) | 60–120 min | VC-1 complete — VC-2 |
| 3 | Network | Firewall, LB, BGP cutover | Network Lead | 60–90 min | Parallel with Phase 2 — VC-3 |
| 4 | Identity | AD, DNS, Certificate Services | Infra Lead (Identity) | 90–120 min | VC-2 + VC-3 — VC-4 |
| 5 | Database | Oracle, Exadata, SQL Server, DB2 | DB Lead | 120–210 min | VC-4 — VC-5 |
| 6 | Middleware | WebSphere, MQ Series | App Lead (Middleware) | 210–240 min | VC-5 — VC-6 |
| 7 | Applications | Tier 0 → Tier 1 → Tier 2 | App Lead | 240–360 min | VC-6 — VC-7 |
| 8 | Mainframe | zSeries LPAR + iSeries | Mainframe Lead | 120–240 min | VC-3 + VC-4 — VC-8 |
| 9 | Job Scheduling | Control-M takeover | Batch Lead | After Phase 7+8 | VC-7 + VC-8 — VC-9 |
| 10 | Business Validation | UAT-level checks + Sign-off | Business Owners | 360+ min | VC-9 — FINAL |

Sequencing Rule Phases 2 and 3 (VMware + Network) run in parallel. Phase 8 (Mainframe) runs in parallel with Phases 2–4. All other phases are strictly sequential. Any phase failure escalates immediately to the Incident Commander before proceeding.

## 5.2  Validation Checkpoint Register

| VC # | Checkpoint Name | Pass Criteria | Validator | Sign-off Required |
| --- | --- | --- | --- | --- |
| VC-0 | DR Declaration | Written authority obtained; war room active; contact list verified | Incident Cmdr | Yes — all leads |
| VC-1 | Storage Ready | All required LUNs/volumes presented at DR site; no replication errors | Storage Team | Yes — Infra Lead |
| VC-2 | Compute Ready | All Tier-0/1 VMs powered on at DR site; no split-brain | VMware Team | Yes — Infra Lead |
| VC-3 | Network Ready | BGP routing live; firewall policies active; LB pool healthy | Network Team | Yes — Network Lead |
| VC-4 | Identity Ready | AD replication confirmed; DNS resolving correctly; auth working | Identity Team | Yes — Infra Lead |
| VC-5 | Databases Ready | All Tier-0/1 DBs open R/W; data integrity checks passed | DB Lead | Yes — DB Lead |
| VC-6 | Middleware Ready | WebSphere app servers running; MQ channels active | App Lead | Yes — App Lead |
| VC-7 | Applications Ready | Tier-0 apps accessible; smoke tests passed | App Lead + Bus. Owner | Yes — App Lead |
| VC-8 | Mainframe Ready | z/OS IPL complete; iSeries subsystems active; CICS/IMS up | Mainframe Lead | Yes — Mainframe Lead |
| VC-9 | Batch/Scheduling Ready | Control-M server live; job definitions imported; no duplicate runs | Batch Lead | Yes — App Lead |
| FINAL | Full DR Operational | All BIA-mandated Tier-0/1 systems validated by business | Business Owners + CTO | Yes — CTO |

# Section 6 — Detailed Step-by-Step Runbooks (Layer-Wise)

## 6.1  Storage Runbook — SAN/NAS Failover

### Preconditions

- SAN replication (EMC SRDF / NetApp SnapMirror) is confirmed in a consistent, replicable state

- DR storage array powered on and healthy; no active alarms on DR storage consoles

- Storage admin credentials verified for DR site arrays

- VC-0 sign-off received from Incident Commander

### Execution Steps

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Confirm replication lag on all Tier-0/1 LUN groups. Log current RPO delta. | EMC SRDF Monitor / SnapCenter | Storage Admin |
| 2 | For SRDF: Issue SRDF/S suspend on Tier-0 LUN groups (synchronous link break) | symrdf suspend -rdfg <group> | Storage Admin |
| 3 | For SnapMirror: Quiesce replication and break mirror on DR volume | snapmirror quiesce / break <vol> | Storage Admin |
| 4 | Mount DR LUNs / NAS volumes on DR compute hosts (ESXi / LPAR / iSeries) | ESXi rescan; HBA zoning validate | Storage + VMware Admin |
| 5 | Run filesystem consistency check on all mounted volumes (fsck / chkdsk) | OS-level or EMC/NetApp tools | Storage Admin |
| 6 | Confirm LUN masking & zoning — only DR hosts can see DR LUNs | EMC Unisphere / ONTAP System Mgr | Storage Admin |
| 7 | Create point-in-time snapshot of all DR volumes (pre-activation baseline) | NetApp Snapshot / EMC TimeFinder | Storage Admin |
| 8 | Log completion time and current RPO delta; update DR dashboard | DR Status Sheet | Storage Admin |

### Validation Checks — VC-1

- All required LUNs visible and mounted on DR compute hosts

- No SRDF or SnapMirror error alerts outstanding

- Filesystem integrity checks completed with zero critical errors

- Pre-activation snapshots confirmed on DR array

- Storage Admin signs off VC-1 in DR log

## 6.2  VMware / SRM Runbook

### Preconditions

- VC-1 (Storage) sign-off received

- DR vCenter and SRM Recovery Server accessible from DR management network

- SRM Recovery Plans validated in last DR drill (no stale VM mappings)

- DR ESXi hosts in connected state with no host-level alarms

### Execution Steps

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Log into DR vCenter; verify all DR ESXi hosts are Connected and in Maintenance Mode | vSphere Web Client | VMware Admin |
| 2 | Exit Maintenance Mode on all DR ESXi hosts | vSphere UI / ESXCLI | VMware Admin |
| 3 | Open SRM at DR site; navigate to Recovery Plans — execute Tier-0 Recovery Plan first | VMware SRM Console | VMware Admin |
| 4 | Monitor SRM plan execution; resolve any VM power-on failures (snapshot dependency check) | SRM Execution Log | VMware Admin |
| 5 | Execute Tier-1 Recovery Plan once Tier-0 VMs validated | VMware SRM Console | VMware Admin |
| 6 | Execute Tier-2 Recovery Plan (non-blocking; lower priority) | VMware SRM Console | VMware Admin |
| 7 | Verify VM-to-network portgroup mapping (ensure DR portgroups are correct, not production) | vSphere Networking | VMware Admin |
| 8 | Confirm vSAN health (if applicable); run cluster health check | vSAN Health Service | VMware Admin |
| 9 | Validate VM-to-storage alignment; ensure no VMs are running on primary site datastores | vSphere Datastore View | VMware Admin |

### Validation Checks — VC-2

- All Tier-0 VMs powered on and heartbeating at DR site

- No split-brain scenarios (VMs active at both sites)

- SRM Recovery Plan execution log shows zero critical failures

- Network portgroup assignments confirmed correct

## 6.3 Network Runbook — Firewall, Load Balancer, Routing

### Preconditions

- DR site network infrastructure powered on and pre-staged (BGP neighbor configured in Idle state)

- Firewall policies pre-loaded and validated in last DR test

- F5 / NSX ALB DR configuration pools pre-staged

- ACI Fabric and DCI with SDWAN validation

### Execution Steps

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Verify DR WAN links are active (MPLS + VPN backup); confirm with ISP if needed | Ping / traceroute / ISP portal | Network Engineer |
| 2 | Activate BGP neighbor at DR site (no-shutdown on BGP session); announce DR subnets | Cisco / Juniper: no shut neighbor <IP> | Network Engineer |
| 3 | Withdraw Primary site BGP route advertisements (or increase AS-PATH to deprioritize) | BGP route policy update | Network Engineer |
| 4 | Activate DR PA/CP firewall policies; verify Security Policy Rulebase is correct revision | Panorama / PA CLI | Network Engineer |
| 5 | Bring up F5 / NSX ALB Virtual Servers at DR site; activate DR pools (point to DR app servers) | F5 TMSH / NSX Manager | Network Engineer |
| 6 | Verify QoS and traffic shaping policies are active for production traffic classes | Cisco QoS / F5 iRules | Network Engineer |
| 7 | Test Internet egress from DR site (outbound connectivity test) | Curl / HTTP test to known endpoints | Network Engineer |
| 8 | Confirm no routing loops or black-holes; run full route verification table review | show ip route / show bgp summary | Network Engineer |

### Validation Checks — VC-3

- BGP session established and DR subnets advertised to upstream providers

- Firewall logging confirms traffic flowing through DR FW policies

- Load balancer pool members show healthy (green) status

- No routing anomalies detected; traceroute from external confirms DR site routing

## 6.4  DNS & Active Directory Runbook

### Preconditions

- VC-3 (Network) sign-off received — DNS must have network connectivity to function

- DR site AD Domain Controllers are pre-staged as replica DCs with full site-link replication

- Split-brain DNS configuration pre-loaded at DR site

### Execution Steps — Active Directory

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Verify DR site DCs are reachable and hold all 5 FSMO roles or FSMO roles have been seized | netdom query fsmo | AD Admin |
| 2 | If primary DCs unreachable, seize FSMO roles on DR DC | ntdsutil seize <role> | AD Admin |
| 3 | Force AD replication from available upstream DC to DR DC | repadmin /syncall /AdePq | AD Admin |
| 4 | Verify AD replication topology — confirm no lingering objects | repadmin /showrepl | AD Admin |
| 5 | Set DR DC as preferred DC for all DR-site workloads (site-link cost adjustment) | AD Sites & Services | AD Admin |

### Execution Steps — DNS

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Activate DR DNS server (Infoblox or Windows DNS) as authoritative for all production zones | DNS Admin Console | Network/DNS Admin |
| 2 | Update DNS A records for all Tier-0/1 application VIPs to DR site IP addresses | Infoblox API / DNS console | DNS Admin |
| 3 | Reduce TTL on critical records to 60 seconds (pre-DR this should already be lowered) | DNS zone edit | DNS Admin |
| 4 | Update internal DNS forwarders to use DR site resolvers | DNS forwarder config | DNS Admin |
| 5 | Validate DNS resolution from multiple DR site hosts for all Tier-0/1 FQDNs | nslookup / dig | DNS Admin |
| 6 | Update external DNS (public-facing) via DNS provider portal / API for public endpoints | DNS provider portal | DNS Admin |

### Validation Checks — VC-4

- All FSMO roles confirmed held by DR DC; no FSMO conflicts

- AD replication showing 0 errors in repadmin /showrepl output

- nslookup for all Tier-0/1 FQDNs returns DR site IP addresses

- LDAP authentication test from DR app server succeeds

## 6.5  Database Runbook — Oracle, Exadata, SQL Server, DB2

### Preconditions

- VC-4 (Identity/DNS) sign-off received

- Database hosts powered on at DR site; OS-level checks passed

- Replication lag / standby apply lag confirmed within RPO

### 6.5.1  Oracle Data Guard Failover

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Confirm Data Guard standby status: verify apply lag < RPO threshold | dgmgrl> show database <db> | DBA |
| 2 | Stop Redo Apply on standby (if needed for controlled failover) | ALTER DATABASE RECOVER MANAGED STANDBY DATABASE CANCEL | DBA |
| 3 | Execute Data Guard Failover (not switchover — primary unavailable) | dgmgrl> failover to <standby_db> | DBA |
| 4 | Open new primary (former standby) with RESETLOGS | ALTER DATABASE OPEN RESETLOGS | DBA |
| 5 | Verify database is open READ WRITE; confirm SCN progression | SELECT STATUS FROM V$INSTANCE | DBA |
| 6 | Update TNS listener and Oracle connection strings for all app tiers to DR DB | tnsnames.ora / JDBC update | DBA + App Lead |

### 6.5.2  Oracle Exadata Specific Steps

- Cell Disk Health: Run cellcli -e list physicaldisk attributes on all DR Exadata storage cells to confirm cell disk status is normal.

- InfiniBand Fabric: Verify InfiniBand connectivity between compute nodes and storage cells — ibstat / ibping on each node.

- ASM Diskgroups: Confirm +DATA and +RECO ASM disk groups mounted READ WRITE on DR Exadata cluster.

- Smart Scan: Execute test Smart Scan query to confirm offloading is active on DR cells.

- Exadata Patching Delta: Confirm DR Exadata is at same patch level as production; note any delta for risk register.

### 6.5.3  SQL Server Always On Failover

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Confirm DR replica synchronization state (Synchronized / Synchronizing) | SQL Server SSMS / T-SQL: SELECT * FROM sys.dm_hadr_database_replica_states | DBA |
| 2 | Execute forced failover on AG (if primary unavailable) | ALTER AVAILABILITY GROUP [AG_Name] FORCE_FAILOVER_ALLOW_DATA_LOSS | DBA |
| 3 | Bring AG databases online at DR replica | ALTER DATABASE [dbname] SET HADR RESUME | DBA |
| 4 | Update AG Listener DNS record to point to DR replica listener IP | DNS + SQL Listener config | DBA + DNS Admin |
| 5 | Run DBCC CHECKDB to confirm database integrity at DR node | DBCC CHECKDB([dbname]) | DBA |

### 6.5.4  DB2 pureScale Failover

- Confirm DB2 cluster services running on DR nodes: db2cluster -cm -list -alert

- If primary CF unavailable, promote secondary CF: db2cluster -cm -set -primary_cf <node>

- Start database: db2start; db2 activate db <DBNAME>

- Validate DB2 log archive path pointing to DR storage

- Execute connection test from application tier host

### Validation Checks — VC-5

- All Tier-0/1 databases open READ WRITE at DR site

- Data integrity checks (DBCC, RMAN validate) passed with zero critical errors

- Application connection string tests successful from middleware/app tier hosts

- RPO validated — confirmed actual data loss within BIA-defined threshold

## 6.6  Middleware Runbook — WebSphere & MQ

### Preconditions

- VC-5 (Databases) sign-off received

- WebSphere profiles and node configurations pre-staged on DR app servers

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Start WebSphere Deployment Manager (DMGR) on DR management host | /opt/IBM/WebSphere/profiles/Dmgr01/bin/startManager.sh | WAS Admin |
| 2 | Verify DMGR started; check SystemOut.log for WSVR0001I (server started) | tail -f SystemOut.log | WAS Admin |
| 3 | Start all managed node agents on DR app server hosts | startNode.sh on each node profile | WAS Admin |
| 4 | Update JNDI datasource JDBC URLs to point to DR database endpoints | WAS Admin Console: Resources > JDBC | WAS Admin + DBA |
| 5 | Update MQ connection factory host/port to DR MQ Manager | WAS Admin Console: Resources > JMS | WAS Admin + MQ Admin |
| 6 | Start MQ Queue Manager on DR host: strmqm <QMGR_NAME> | MQ CLI | MQ Admin |
| 7 | Activate MQ channel listeners; verify sender/receiver channels are running | runmqsc: DISPLAY CHSTATUS(*) | MQ Admin |
| 8 | Start WebSphere application servers in dependency order (Core → Supporting) | startServer.sh <server_name> | WAS Admin |
| 9 | Verify application deployment: check WAS SystemOut for app started messages | grep 'CWWKZ0001I' SystemOut.log | WAS Admin |

### Validation Checks — VC-6

- All WAS managed servers showing 'Started' in DMGR console

- JDBC datasource test connections successful from WAS admin console

- MQ Queue Manager running; no dead-letter queue accumulation

- Health check URL for each application endpoint returns HTTP 200

## 6.7  Application Layer Runbook

### Preconditions

- VC-6 (Middleware) sign-off received

- Application dependency map consulted — startup order strictly followed

### Application Recovery Sequence by Tier

| Tier | Application | Start Sequence | Start Script / Method | Validation Test |
| --- | --- | --- | --- | --- |
| Tier 0 | Core Banking System | 1st — no dependencies | systemctl start cbs-service | Login + transaction test |
| Tier 0 | Payment Gateway | 2nd — depends on Core Banking | ./start_pgw.sh | End-to-end payment smoke test |
| Tier 1 | ERP (SAP / Oracle EBS) | 3rd — depends on Oracle DB + WAS | SAP Start / adstrtal.sh | Login + module access test |
| Tier 1 | CRM | 4th — depends on SQL Server + WAS | Service start | Login + customer record fetch |
| Tier 1 | Customer Portal | 5th — depends on CRM + LB | ./start_portal.sh | External URL response test |
| Tier 2 | HR System | 6th — depends on AD + SQL Server | systemctl start hr-app | Login test |
| Tier 2 | Reporting / BI | 7th — depends on all DBs | Cognos / BO start | Report generation test |

### Validation Checks — VC-7

- All Tier-0 application smoke tests passing

- All Tier-1 applications accessible with no authentication failures

- Load balancer health checks showing all app pool members healthy

- End-to-end transaction test (golden transaction set) executed and passed

## 6.8  Mainframe Runbook — IBM zSeries & iSeries (AS400)

### 6.8.1  zSeries (z/OS)

### Preconditions

- VC-3 (Network) + VC-4 (Identity) sign-off received

- DR LPAR pre-configured; GDPS control has already suspended replication and journaling is current

- DR z/OS system programmer available

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | PRE-FAILOVER: Confirm any new libraries added to APF/LNKLST are in PROG30 member; confirm OMVS mounts in BPXPARM; confirm LPA changes in LPALST30 | Compare PROG30/BPXPRMFP/LPALST30 vs active | Mainframe Sysprog |
| 2 | Verify DR z16 HMC LPAR configs: CPU counts, weights, ZIIP assignments match DR profile (Operational Customizations > Activation Profiles) | HMC Web Console | Mainframe Sysprog |
| 3 | Access GDPS console; confirm XRC/PPRC replication is suspended and journals are current; validate PowerMax storage group RDF is in Adaptive Copy / Failed Over state | GDPS ISPF panels / Unisphere | Mainframe Sysprog |
| 4 | JES2 CHECKPOINT OFFLOAD before shutting down primary sysplex: offload CKPT1 from CF to DASD so checkpoint survives LPAR shutdown $D CKPTDEF $T CKPTDEF,NEWCKPT1=(DSN=SYS1.HASPCKPT,VOL=SYSxM0) $TCKPTDEF,RECONFIG=YES (Reply 1 then CONT) $D CKPTDEF (verify CKPT1 is now DASD-based) | $T CKPTDEF / $TCKPTDEF | Mainframe Sysprog |
| 5 | Shutdown primary sysplex LPARs in order: JESC → JESA → JESB (ensure checkpoint offload complete before $PJES2 on last LPAR). Deactivate all LPARs: JESC, JESA, JESB, XCFA00, XCFB00, MV3A, MV3B, MV3C, XCFA01, XCFB01 | HMC: Deactivate LPAR | Mainframe Sysprog |
| 6 | Execute PowerMax DASD failover (R2→R1 reverse replication stop at step 33) and DD/DLm failover in parallel | PowerMax Siteswap / DLm procedure | Storage Admin |
| 7 | Startup EMER LPAR at DR site (Load address per DR IODF). Respond to prompts: 00,C (memory); RACF ##,continue (twice); JES2 init ##,warm,noreq; S TSO after VTAM is active | HMC Power On / EMER console | Mainframe Sysprog |
| 8 | Validate EMC tasks on DR system: S EMCSCF4 (wait), then S EMCRDF. Check for owed tracks on JES2/MVS3 SGs: #SQ VOL,40C0,INV_TRKS | EMCSCF4 / EMCRDF / #SQ | Mainframe Sysprog |
| 9 | Pre-JESB IPL: reinitialize TEMP volumes using TEMPOFF, TEMPIN9J (UNIT=4xxx), TEMPONL, TEMPVVDJ, then TEMPOFF to vary offline all but required 5 packs. Verify unit 4200 (SYS111) and 4000 (SYSCOM) are online. | SYS1.DISASTER.CNTL(TEMPOFF/TEMPIN9J/TEMPONL) | Mainframe Sysprog |
| 10 | Activate XCFB00 CF LPAR at DR site. Then activate JESB, JESA, JESC LPARs | HMC: Activate LPAR | Mainframe Sysprog |
| 11 | IPL DR LPAR from DR DASD. Respond to IPL console messages: IXC420D → R 0,I (initialize sysplex) CFRM couple dataset prompts → R 0,C then R 0,U (twice) $HASP426 → R #,WARM,NOREQ $HASP479 → R #,Y (bypass multi-member integrity lock) | HMC Console / F600 | Mainframe Sysprog |
| 12 | IPL verification: D OMVS (confirm ACTIVE); D XCF (JESB in CF); D XCF,STR; D GRS (confirm GRS STAR MODE); D SMS,SHCDS (Status GOOD/ACTIVE); D RRS,URSTATUS | MVS console commands | Mainframe Sysprog |
| 13 | Start VTAM, TCPIP, and all automation rules: F CONTROLO,F=SYS2.IOAO.RULES(IPLMINI). Clean TEMP catalog: SYS1.DISASTER.CNTL(DELTMPGN). Verify network ports FC/FD/F8/F9 online. | F CONTROLO / console | Mainframe Net Admin |
| 14 | DB2 Recovery: Start all DB2T subsystems (/@DBT1 START DB2, /@DBT2 START DB2, /@DBT3 START DB2). Submit SYS1.DISASTER.DB2(DRGRECT) — repeat until SYSTSPRT contains only READY and END. Then stop DBT2/DBT3 and restart DBT1. Repeat same procedure for DB2P subsystems using DRGRECP. | /@DBx START/STOP DB2 / DRGRECT / DRGRECP | DB2 z/OS DBA |
| 15 | MQ Recovery: Start MQT2 (/MQT2 START QMGR), recover structures (OPR.PERM.CNTL(MQSRECT2)), then start MQT3. Stop both, restart MQT2. Start MQT2 trigger monitor (/S MQTRGYYB). Repeat for MQP2/MQP3 using MQSRECP2. Start MQPABKUP backup, then /S MQTRGXXB. | /MQx START QMGR / MQSRECT2 / MQSRECP2 | MQ Admin |
| 16 | Start non-QSG queue managers: /MQGA START QMGR, /S MQGAAGT; /MQFA START QMGR, /S MQFAAGT; /MQB1 START QMGR. Start Mainview: S MVSTART. | /MQxx START QMGR / MVSTART | MQ Admin |
| 17 | IPL JESA then JESC LPARs using same load address and IODF. Apply F CONTROLO rules (IPLSECND, IPLJESC). Validate started tasks: SYS2.SYSTEMS.JOBS(STCVER). Run ping tests for JESA and JESC. | HMC / F CONTROLO / STCVER | Mainframe Sysprog |
| 18 | Start CICS in dependency order: /S J,N=CICSGO1 (TSQ/CMSA — wait for CMAS init complete); CICSGO2 (WUSA/APPL — wait for WUI init); CICSGO3 (Terminal tasks); CICSGO4 (EXCI interface). Initialize Temp Storage: MC.PERM.JCL(DSTSQ01J). Open CICS files: SSY0OPEN, NRIOPEN, CICSTCP. | /S J,N=CICSGOx / DSTSQ01J | CICS Admin |

### 6.8.2  iSeries / AS400 (IBM i)

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | PRE-FAILOVER (Friday): Disable MIMIX audits — run ETS50050 *DISABLE. Hold Saturday Jobs: RE020SAT, RE030SAT, RE040SAT | Robot Schedule / ETS50050 | IBM i Admin |
| 2 | Sign on to CONSOLE as QSECOFR on source PRODDSS/Prod partition. Establish Teams bridge and confirm all IBM i consoles are accessible. | IBM i Access Client / TN5250 | IBM i Admin |
| 3 | Change DNS: update PRODDSS and RODS hostname to point to DR partition IP. Flush DNS cache on affected clients (ipconfig /flushdns). Confirm ping: RODS.APPN.SNA.IBM.COM ; PRODDSS.APPN.SNA.IBM.COM | DNS Console / ipconfig /flushdns | IBM i Admin / Network |
| 4 | End Robot Schedule on source partition: rbo > 1 > 3 > 2 | Robot Schedule menu | IBM i Admin |
| 5 | End MIMIX replication on PRODE: MIMIX/ENDMMX (press Enter). Monitor MIMIX/WRKDG on all nodes until all data groups are down — end manually if needed after 10 minutes. Verify MIMIX/WRKSYS shows *INACTIVE on all nodes. | MIMIX/ENDMMX / WRKDG / WRKSYS | IBM i Admin |
| 6 | End MIMIX SBS on source PRODDSS/Prod (should show 2 ports): ENDSBS SBS(MIMIXSBS) OPTION(*IMMED). End MIMIX SBS on PRODDSS/HA (should show 1 port): ENDSBS SBS(MIMIXSBS) OPTION(*IMMED). Kill remaining SBS ports on all nodes. | ENDSBS SBS(MIMIXSBS) OPTION(*IMMED) | IBM i Admin |
| 7 | Deactivate floating TCP interface on source: ENDTCPIFC INTNETADR('10.7.1.169'). Verify ended: NETSTAT OPTION(*IFC). Take Before image for documentation. | ENDTCPIFC / NETSTAT OPTION(*IFC) | IBM i Admin |
| 8 | Activate floating TCP interface on DR target partition: STRTCPIFC INTNETADR('10.7.1.169'). Verify active: NETSTAT OPTION(*IFC). Take After image. | STRTCPIFC / NETSTAT OPTION(*IFC) | IBM i Admin |
| 9 | Start Role Swap — logoff and back on as QSECOFR on source. Run WRKCLRU. Execute QZRDPWRHA/CHKDUPLIBS IASP(DSSIASP) (addlibl QZRDPWRHA and QZRDHASM first). Run QSYS/WRKASPJOB and end all jobs. | WRKCLRU / CHKDUPLIBS / WRKASPJOB | IBM i Admin |
| 10 | Verify DSSDEVCRG Resource Group: Option 9 — confirm Active and Primary Node is correct. Verify ASP Copy: Option 10 > Option 25 on source IASP — confirm ASP Copy is correct. | WRKCLRU Option 9 / Option 10 | IBM i Admin |
| 11 | Ensure QBATCH is active on all 4 nodes: start SBS QBATCH in QSYS if not running. Initiate role swap: WRKCLRU > Option 9 > Option 3=Change primary > DSSDEVCRG. | STRSBS SBSD(QSYS/QBATCH) / WRKCLRU | IBM i Admin |
| 12 | Monitor role swap progress: on source ASP State goes to VARYOFF (~2 min). On target PRODDSS/DR ASP State goes to AVAILABLE (~1.5 min). Once role swap job ends on source, verify on target. | WRKASPJOB / DSPDTAARA on both partitions | IBM i Admin |
| 13 | Verify direction of replication has switched on all 4 nodes. Verify cluster is active on all 4 nodes: WRKCLRU — all nodes showing Active. | WRKCLRU / cluster node status | IBM i Admin |
| 14 | Verify 3rd party software on DR partition. Apply Turnover key: IFS KEY at /home/unicom/licenses/TN4/*. Start TSERVER subsystem if not started: STRSBS SBSD(QGPL/TSERVER). Run SOFTTUNE/TWRKLIC and change PRODDSS serial number to *LOCAL. | SOFTTUNE/TWRKLIC / IFS Key apply | IBM i Admin |
| 15 | Robot Schedule restart on DR partition: run RBTSYSLIB/RSLSHUTDWN to stop RBTSLEEPER. Run RSLSETOID PRC(RBT). Start STRSBS SBSD(RBTSYSLIB/RBTSLEEPER). | RSLSHUTDWN / RSLSETOID / STRSBS | IBM i Admin |
| 16 | Verify all expected subsystems are active on DR partition (see SBS validation checklist). Verify all TCP servers and host servers that should be active are running. | WRKSBSSTSE / WRKTCPSTS | IBM i Admin |
| 17 | Host table changes on ALL nodes (PRODDSS/HA, PRODDSS/Prod, PRODE, PRODA, DEVA, DEVA/HA): RMVTCPHTE for old IPs; ADDTCPHTE for new DR IPs with correct hostname aliases (PRODDSS, PRODDSS.APPN.SNA.IBM.COM, RODS, MSDSS, MXVPRDSS, BRMSDSS). | RMVTCPHTE / ADDTCPHTE on each node | IBM i Admin |
| 18 | Turn over to application teams for testing. Run file count query: RUNQRY ZMARY/ROLECNTSPE on DR partition to capture pre-MIMIX counts. | RUNQRY ZMARY/ROLECNTSPE | IBM i Admin / App Teams |
| 19 | Start MIMIX replication from PRODE/Prod to PRODDSS/HA: verify MIMIX SBS started on PRODE and PRODA; start MIMIX SBS on source (1 port); start MIMIX SBS on target (2 ports). Start STRMMX on PRODE. Update ADDRDBDIRE for floating IP. | STRSBS MIMIXQGPL/MIMIXSBS / STRMMX / ADDRDBDIRE | IBM i Admin |
| 20 | Post-role-swap housekeeping: Run Robot Schedule — display missed jobs and DO on ETS50020 Terminated jobs. Release Saturday Jobs (RE020SAT, RE030SAT, RE040SAT). Release ETS50051 *ENABLE MIMIX audits. Update Robot Network node: RBNCFGNODE HOSTIP('<DR_IP>') AHOSTIP(*NONE); RBNSTRNODE. | Robot Schedule / ETS50051 / RBNCFGNODE | IBM i Admin |

### Validation Checks — VC-8

- z/OS IPL complete; CICS, IMS, DB2 z/OS, MQ all showing active status

- JES2 spool operational; no outstanding console messages requiring response

- IBM i subsystems active (QBATCH, QINTER, QSRV, MIMIXSBS, RBTSLEEPER, TSERVER all running); application libraries verified via CHKOBJ

- IBM i role swap confirmed: IASP AVAILABLE on DR partition; MIMIX replication direction verified; Robot Schedule active; DNS resolved to DR IPs; 5250 session test from DR terminal gateway passing

## 6.9  Job Scheduling Runbook — BMC Control-M

### Preconditions

- VC-7 and VC-8 sign-offs received (applications + mainframe operational)

- Control-M/EM (Enterprise Manager) at DR site is pre-installed and licensed

- Control-M job definitions exported from primary site (latest backup available)

| # | Step | Tool / Command | Owner |
| --- | --- | --- | --- |
| 1 | Start Control-M/Server at DR site | systemctl start ctmserver | Batch Admin |
| 2 | Start Control-M/EM (Enterprise Manager) at DR site | systemctl start ctmem | Batch Admin |
| 3 | Import latest job definitions from backup (XML/CTM definition export) | ctm deploy definitions import -f <file> | Batch Admin |
| 4 | CRITICAL: Disable any batch jobs that TARGET primary-site resources or DB connections | ctm config server:batch disable <job> | Batch Admin + App Lead |
| 5 | Update all job definitions with DR site resource targets (DB endpoints, file paths, UNC paths) | CTM Edit in EM / XML edit | Batch Admin + DBA |
| 6 | Configure Control-M for z/OS agent on DR z/OS LPAR | zOS: CTMLIST / CTMIM | Batch Admin + Mainframe |
| 7 | Configure Control-M for iSeries agent on DR IBM i partition | IBM i: ADDCTMAGENT | Batch Admin + IBM i |
| 8 | Set New Day date/order date correctly (DO NOT restart already-completed jobs) | ctm config activenet set_odate | Batch Admin |
| 9 | Start with critical batch jobs only; obtain business sign-off before releasing full schedule | CTM Order/Force | Batch Admin + Business |

CRITICAL — Duplicate Job Prevention Before releasing any batch jobs at DR site, confirm with business teams which jobs have ALREADY COMPLETED on the primary site for the current business day. Running duplicate batch cycles (especially financial postings, GL closes, billing) can cause irreversible data corruption.

### Validation Checks — VC-9

- Control-M/EM console showing all agents Connected

- Critical batch job definitions imported and targeting DR resources

- No duplicate jobs running on both primary and DR environments

- First critical batch job executed successfully end-to-end as proof-of-concept

# Section 7 — Dependency Mapping & Application Grouping

## 7.1  Tier-wise Recovery Groups

| Tier | Application Group | Upstream Dependencies | Downstream Dependents | Recovery Wave |
| --- | --- | --- | --- | --- |
| Tier 0 | Core Banking, Payment GW | Storage, Network, AD, Oracle Exadata | ERP, CRM, Customer Portal | Wave 1 (0–4 hrs) |
| Tier 1 | ERP, CRM, Customer Portal | WAS, SQL Server, Oracle, DNS, AD | HR, Reporting, Batch | Wave 2 (4–8 hrs) |
| Tier 2 | HR, Reporting, BI | AD, SQL Server, Tier-1 Apps | None (terminal tier) | Wave 3 (8–24 hrs) |
| Tier 3 | Dev/Test Mirrors, Archive | Storage only | None | Wave 4 (24–48 hrs) |

## 7.2  Critical Dependency Chain

The following chain represents the minimum dependency path for Tier-0 recovery. Any break in this chain stops recovery:

Storage (SAN LUNs) → ESXi Hosts → Network Fabric → Firewall → DNS → AD → Oracle/Exadata → WebSphere → Core Banking App → Payment Gateway Each arrow represents a hard dependency. Parallel tracks: Mainframe chain runs independently alongside the above.

# Section 8 — Validation & Sign-off

## 8.1  Technical Validation Checklist

| Validation Item | Responsible Team | Status | Sign-off |
| --- | --- | --- | --- |
| Storage: All Tier-0/1 LUNs mounted and consistent | Storage Team | [ ] |  |
| VMware: All Tier-0/1 VMs powered on; no split-brain | VMware Team | [ ] |  |
| Network: BGP routing active; firewall + LB operational | Network Team | [ ] |  |
| DNS: All FQDNs resolving to DR site IPs | DNS Admin | [ ] |  |
| AD: FSMO roles on DR DC; replication healthy | AD Admin | [ ] |  |
| Oracle / Exadata: Primary failover; READ WRITE mode | DBA Team | [ ] |  |
| SQL Server: AG failover; DBCC CHECKDB passed | DBA Team | [ ] |  |
| DB2: Cluster services active; DB activated | DBA Team | [ ] |  |
| WebSphere: All managed servers started; JDBC tests pass | WAS Admin | [ ] |  |
| MQ: Queue Manager running; channels active | MQ Admin | [ ] |  |
| Applications Tier-0: Smoke tests passed | App Lead | [ ] |  |
| Applications Tier-1: Accessibility confirmed | App Lead | [ ] |  |
| Mainframe zSeries: CICS / IMS / DB2 z/OS active | Mainframe Lead | [ ] |  |
| iSeries: Subsystems active; 5250 session test passed | IBM i Admin | [ ] |  |
| Control-M: Agents connected; critical jobs validated | Batch Lead | [ ] |  |

## 8.2  Business Validation (UAT-Level Checks)

| Business Test | Business Owner | Expected Result | Sign-off |
| --- | --- | --- | --- |
| Core Banking: End-to-end transaction (debit/credit cycle) | Banking Operations | Transaction committed | / / ___ |
| Payment Gateway: Test payment (sandbox) | Finance / Payments Team | Payment authorized | / / ___ |
| ERP: Create and post test purchase order | Finance / Procurement | PO posted successfully | / / ___ |
| CRM: Retrieve and update customer record | Customer Service | Record retrieved / updated | / / ___ |
| Customer Portal: External login and profile view | Digital / IT Ops | Login successful | / / ___ |
| Reporting: Generate prior-day financial report | Finance | Report generated correctly | / / ___ |

## 8.3  Final DR Operational Sign-off

| Role | Name | Date/Time | Signature |
| --- | --- | --- | --- |
| Incident Commander |  |  |  |
| Infrastructure Lead |  |  |  |
| Application Lead |  |  |  |
| Database Lead |  |  |  |
| Mainframe Lead |  |  |  |
| Business Owner (Tier-0) |  |  |  |
| CTO / DR Program Director |  |  |  |

# Section 9 — Communication Templates

## Template 1 — DR Invocation Notification

SUBJECT: [CONFIDENTIAL] DISASTER RECOVERY DECLARED — [Company] — [Date / Time] UTC To: Executive Leadership, All IT Leads, Business Continuity Team 1. SITUATION: [Brief description of incident — e.g., Primary Data Center inaccessible due to [cause]]. 2. DECLARATION: As of [TIME] UTC on [DATE], the Disaster Recovery Plan has been formally invoked by [Name / Role]. 3. ACTION: Failover to DR Site — [City B Data Center] — is now in progress per the DR Failover Playbook v1.0. 4. IMPACT: [Systems affected / currently unavailable]. Estimated recovery: Tier-0 by [Time], Tier-1 by [Time]. 5. WAR ROOM: Bridge line active — [Dial-in details]. Next update in 60 minutes. [Name] ¦ Incident Commander ¦ [Phone] ¦ [Email]

## Template 2 — 60-Minute Status Update

SUBJECT: DR STATUS UPDATE #[N] — [Time] UTC ¦ [Green/Amber/Red] OVERALL STATUS: [GREEN / AMBER / RED] Completed: [List completed phases] In Progress: [Current phase + responsible team] Issues / Blockers: [Any deviations from plan; mitigating actions] ETA to Next Milestone: [Phase X completion by Time] Next Update: [Time]. Incident Commander: [Name]

# Section 10 — Risks & Known Constraints

## 10.1  DR Risk Register

| # | Risk Description | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | SRDF replication lag exceeds RPO at time of failover | Medium | High | Monitor lag continuously; trigger DR alert at 50% of RPO | Storage Lead |
| R2 | SRM Recovery Plan fails due to stale VM mappings | Medium | High | Quarterly SRM test drill; keep protection groups updated | VMware Lead |
| R3 | DNS TTL not pre-reduced before failover; propagation delay | High | Medium | Pre-DR checklist includes TTL reduction to 60s; verify in drills | DNS Admin |
| R4 | AD FSMO role seizure causes USN rollback / AD inconsistency | Low | Critical | Use ntdsutil carefully; validate with repadmin post-seizure | AD Admin |
| R5 | Oracle Data Guard failover with data loss beyond RPO | Low | Critical | Monitor apply lag; use DGMGRL health checks; test monthly | DBA Lead |
| R6 | Control-M duplicate batch jobs at both sites | High | Critical | Documented disable procedure + business confirmation mandatory | Batch Lead |
| R7 | Mainframe GDPS takeover timeout / journal gap | Medium | High | Test GDPS annually; coordinate with IBM support during DR | Mainframe Lead |
| R8 | DR site WAN link degraded — insufficient bandwidth | Medium | High | Pre-test WAN capacity; ISP SLA for priority routing | Network Lead |
| R9 | Key personnel unavailable during actual disaster | Medium | High | Minimum 2 trained per role; documented contact alternates | DR Program Dir |
| R10 | Exadata patch level delta between primary and DR | Medium | Medium | Monthly DR patch parity check; log delta in risk register | DBA Lead |

## 10.2  Known Manual Interventions Required

- FSMO role seizure (Active Directory) — fully manual; no automation available

- SRDF group suspend — requires manual execution by EMC-certified Storage Admin

- Exadata cell health verification — requires physical/SSH access to each storage cell

- Control-M job audit (duplicate prevention) — requires human judgment; cannot be automated

- Mainframe IPL console responses — requires trained z/OS system programmer on-call

- iSeries journal application (APYJRNCHG) — requires IBM i Admin to monitor and guide

# Section 11 — Failback Strategy (High Level)

## 11.1  Conditions for Failback

- Primary site physically restored and certified by Facilities & Infrastructure teams

- Primary site systems passed full infrastructure health assessment (storage, power, cooling, network)

- Business authorization received from CTO and Business Owners to initiate failback

- Minimum 72-hour stability window at DR site before failback is initiated

- Planned failback window approved via Change Management (emergency CAB if required)

## 11.2  Failback Sequence Overview

| Seq | Activity | Key Action | Note |
| --- | --- | --- | --- |
| 1 | Primary Site Rebuild | Hardware, OS, and infrastructure validated | Do NOT remove DR configuration until failback complete |
| 2 | Reverse Replication | Re-establish storage replication from DR → Primary | Allow sync to complete; validate data integrity |
| 3 | Planned Switchover (not failover) | Controlled switchover using Oracle DG switchover, SRM re-protect | Zero data loss path — preferred over failover |
| 4 | Network Cutback | Repoint BGP, DNS, LB to primary site | Test all routes before cutting traffic |
| 5 | Application Validation | Full BIA test set run at primary site | Business sign-off required before declaring primary live |
| 6 | DR Site Decommission (temporary) | Remove DR-specific configs; re-stage DR for next event | Control-M: re-point to primary; disable DR agents |
| 7 | Lessons Learned | Post-incident report within 5 business days | Update playbook; update DR risk register |

Failback Principle Failback is treated as a planned, change-managed activity — NOT an emergency. The organization should be prepared to operate from the DR site for weeks if necessary. Never rush failback under pressure; an unstable failback can result in a secondary outage.

# Section 12 — Failover Timeline View (Hour-by-Hour)

## 12.1  Target Timeline — Tier-0 RTO: 4 Hours | Tier-1 RTO: 8 Hours

| Time Window | Phase | Responsible Team | Key Actions & Milestones |
| --- | --- | --- | --- |
| H+0:00–H+0:30 | Pre-Failover (Phase 0) | Incident Cmdr + All Leads | DR declared; war room active; all leads on bridge; VC-0 signed |
| H+0:30–H+1:00 | Storage Failover (Phase 1) | Storage Team | SRDF suspend; SnapMirror break; LUNs presented; snapshots taken; VC-1 |
| H+1:00–H+2:00 | VMware Failover (Phase 2) | VMware Team | SRM Tier-0 plan executed; Tier-1 plan executed; VMs validated; VC-2 |
| H+1:00–H+1:45 | Network Cutover (Phase 3) [Parallel] | Network Team | BGP activated; firewall policies live; LB pools healthy; VC-3 |
| H+1:00–H+2:30 | Mainframe IPL (Phase 8) [Parallel] | Mainframe Team | z/OS IPL; JES2/VTAM/CICS/IMS start; iSeries subsystems active; VC-8 |
| H+2:00–H+2:30 | AD / DNS Cutover (Phase 4) | Identity + DNS Team | FSMO verified; AD replication confirmed; DNS updated; VC-4 |
| H+2:30–H+3:30 | Database Failover (Phase 5) | DBA Team | Oracle DG failover; Exadata health; SQL AG failover; DB2 start; VC-5 |
| H+3:30–H+4:00 | Middleware Recovery (Phase 6) | WAS + MQ Team | DMGR up; node agents up; JDBC updated; MQ channels active; VC-6 |
| H+4:00–H+5:00 | Tier-0 Apps (Phase 7a) | App Lead + Bus. Owners | Core Banking + Payment GW live; business smoke test; VC-7 (Tier-0) |
| H+5:00–H+7:00 | Tier-1 Apps (Phase 7b) | App Lead + Bus. Owners | ERP, CRM, Customer Portal live; business validation; VC-7 (Tier-1) |
| H+7:00–H+8:00 | Control-M Activation (Phase 9) | Batch Lead | Control-M live at DR; critical jobs released; duplicate check done; VC-9 |
| H+8:00+ | Tier-2 Apps + Full Business Val. | App Lead + All BUs | Full business validation; FINAL sign-off by CTO; DR declared operational |

# Section 13 — Single-Page DR Execution Dashboard

This dashboard is updated by the Incident Commander every 30 minutes during DR execution and shared with executive leadership.

| DR DECLARED: [Date / Time UTC] | INCIDENT COMMANDER: [Name] | CURRENT STATUS: AMBER |
| --- | --- | --- |

| Phase / Layer | Status | VC # | ETA / Completed | Owner |
| --- | --- | --- | --- | --- |
| Pre-Failover / Governance | COMPLETE | VC-0 | H+0:25 | Incident Cmdr |
| Storage (SAN/NAS) | COMPLETE | VC-1 | H+0:58 | Storage Team |
| VMware / SRM | IN PROGRESS | VC-2 | H+2:00 ETA | VMware Team |
| Network / Firewall / LB | IN PROGRESS | VC-3 | H+1:45 ETA | Network Team |
| Mainframe (z/OS + iSeries) | IN PROGRESS | VC-8 | H+2:30 ETA | Mainframe Team |
| Active Directory / DNS | PENDING | VC-4 | Awaiting VC-2/3 | Identity Team |
| Databases (Oracle/SQL/DB2) | PENDING | VC-5 | Awaiting VC-4 | DBA Team |
| Middleware (WebSphere/MQ) | PENDING | VC-6 | Awaiting VC-5 | WAS/MQ Team |
| Applications Tier-0 | PENDING | VC-7 | Awaiting VC-6 | App Lead |
| Applications Tier-1 | PENDING | VC-7 | Awaiting Tier-0 | App Lead |
| Job Scheduling (Control-M) | PENDING | VC-9 | Awaiting VC-7/8 | Batch Lead |
| Business Validation / FINAL | PENDING | FINAL | TBD | Business Owners |

| OPEN ISSUES / BLOCKERS 1. VMware SRM — 2 VMs (appsvr03, appsvr07) failing to power on. Root cause: snapshot lock. ETA fix: 15 min. 2. DR WAN MPLS link showing 40% packet loss. ISP engaged. Backup VPN active. 3. Mainframe IPL console waiting for REPLY response — Mainframe Sysprog responding. | DR METRICS SNAPSHOT Elapsed Time: H+1:15 since DR Declaration Phases Complete: 2 of 10 (VC-0, VC-1) Actual RPO (Storage): 18 minutes (within 30-min target) Tier-0 RTO Target: H+4:00 ¦ Current Projection: H+4:30 (AMBER) Next Executive Update: H+2:00 UTC |
| --- | --- |

# Appendix A — Contact List

| Role | Name | Mobile | Email | Alternate |
| --- | --- | --- | --- | --- |
| Incident Commander | [Name] | [+XX] | [email] | [Backup Name] |
| DR Program Director | [Name] | [+XX] | [email] | [Backup Name] |
| Infrastructure Lead | [Name] | [+XX] | [email] | [Backup Name] |
| Storage Admin | [Name] | [+XX] | [email] | [Backup Name] |
| VMware Admin | [Name] | [+XX] | [email] | [Backup Name] |
| Network Engineer | [Name] | [+XX] | [email] | [Backup Name] |
| DNS / AD Admin | [Name] | [+XX] | [email] | [Backup Name] |
| Database Lead (Oracle) | [Name] | [+XX] | [email] | [Backup Name] |
| Database Admin (SQL/DB2) | [Name] | [+XX] | [email] | [Backup Name] |
| WAS / Middleware Admin | [Name] | [+XX] | [email] | [Backup Name] |
| Application Lead | [Name] | [+XX] | [email] | [Backup Name] |
| Mainframe Sysprog | [Name] | [+XX] | [email] | [Backup Name] |
| IBM i / AS400 Admin | [Name] | [+XX] | [email] | [Backup Name] |
| Control-M / Batch Lead | [Name] | [+XX] | [email] | [Backup Name] |
| CISO | [Name] | [+XX] | [email] | [Backup Name] |
| CTO | [Name] | [+XX] | [email] | [Backup Name] |

# Appendix B — Tooling References

| Tool / Platform | Vendor | Purpose | Access URL / Console |
| --- | --- | --- | --- |
| EMC SRDF Monitor | Dell EMC | Storage replication monitoring | https://[DR-EMC-IP]/Unisphere |
| NetApp ONTAP Mgr | NetApp | NAS/SnapMirror management | https://[DR-NETAPP-IP]/ontap |
| VMware vCenter (DR) | VMware | DR VM management | https://[DR-VCENTER-FQDN] |
| VMware SRM | VMware | Failover orchestration | Integrated in DR vCenter |
| Panorama / PA | Palo Alto | Firewall policy management | https://[PANORAMA-FQDN] |
| F5 BIG-IP TMUI | F5 Networks | Load balancer management | https://[DR-F5-MGMT-IP] |
| Infoblox DDI | Infoblox | DNS/IPAM management | https://[INFOBLOX-FQDN] |
| Oracle DGMGRL | Oracle | Data Guard failover CLI | SSH to DR DB host |
| IBM HMC | IBM | Mainframe partition management | https://[HMC-DR-IP] |
| Control-M/EM | BMC Software | Batch scheduling EM console | https://[CTM-DR-FQDN]:9000 |
| DR Status Dashboard | Internal | Real-time DR execution tracking | https://[DR-PORTAL-URL] |

# Appendix C — DR Drill Learnings Log

| Drill Date | Scenario Tested | Finding / Gap | Remediation & Status |
| --- | --- | --- | --- |
| [DD/MM/YYYY] | Full Failover DR1 | SRM recovery plan had 3 stale VM entries causing delay | VM protection groups updated — CLOSED |
| [DD/MM/YYYY] | Database Failover | Oracle DG apply lag was 45 min — exceeded RPO | Tuned redo log transport; RPO now 18 min — CLOSED |
| [DD/MM/YYYY] | Control-M Cutover | Duplicate batch jobs ran on both sites | Documented dual-disable procedure — CLOSED |
| [DD/MM/YYYY] | Mainframe IPL | IPL took 90 min vs 60 min target | LPAR warm restart procedure documented — IN PROGRESS |
| [Add new rows per drill] |  |  |  |

END OF DOCUMENT Enterprise DR Failover Playbook v1.0 ¦ CONFIDENTIAL ¦ Review Date: Quarterly